## Overview
multiship — Combined Shipment-Validation Report
Client MKL246 · 4 test runs (UPS & FedEx, domestic & international) · validate-only · 26–27 September 2026
BOTTOM LINE: Domestic shipping is solid on both carriers. International is split — FedEx international works, but UPS international is a TOTAL BLOCKER (every lane fails). One critical bug (UPS ShipmentContentsValue) and one high-severity export-filing failure (FedEx→China) remain open. See the Failures & Defects register.
Test scorecard
Test run | Date | Runs | Clean pass | Pass w/ warning | Outright fail | Verdict
UPS — Domestic | 26 Sep | 26 | 20 | 0 | 6 | PASS (config gap)
FedEx — Domestic | 26 Sep | 40 | 34 | 6 | 0 | PASS
UPS — International | 27 Sep | 21 | 0 | 0 | 21 | BLOCKED — all fail
FedEx — International | 27 Sep | 31 | 13 | 12 | 6 | WORKS (2 issues)
TOTAL |  | 118 | 67 | 18 | 33 | 118 runs · 33 failures
The two open issues that block shipping
① UPS International — invalid ShipmentContentsValue [P1 CRITICAL, OPEN]
Every US→international UPS shipment fails at the live carrier (Time-in-Transit) check: 'invalid ShipmentContentsValue'. All other checks pass. Independent of country, service and packaging → blocks 100% of UPS international. Fix: build the TNT ShipmentContentsValue as MonetaryValue + CurrencyCode from the commercial-invoice total.
② FedEx International → China — AES/EEI export filing [P2 HIGH, OPEN]
US→CN fails on BOTH FedEx international services: 'The FTR Exemption or AES Citation you provided is not valid for EEI.' Other destinations (CA/GB/AU/BR/IN) pass at the same value → China-specific export-control rule. Fix: capture an AES ITN, or set the correct FTR exemption, for controlled destinations.
Context: all runs are validate-only (no labels bought), client MKL246, ship-from 3PL-EAST (Zeeland, MI). Sandbox carrier accounts UPS 746W05 / FedEx 740561111. Full per-test detail on the Deep Dive tab; every failure and defect (open and resolved) is itemised on the Failures & Defects tab. Source: the four standalone report workbooks.

## Failures & Defects
Failures & Defects Register — all 4 test runs
Ranked by severity. Covers outright failures and backend defects (open and resolved).
ID | Severity | Test | Category | What happened / error | Root cause | Scope / blast radius | Status | Fix / action
F1 | P1 Critical | UPS International | Backend / carrier | Carrier check fails on EVERY lane: 'UPS Time-in-Transit rejected the request: invalid ShipmentContentsValue'. All 4 prior checks pass. | TNT request sends ShipmentContentsValue in a shape UPS rejects (needs a monetary value + currency from the invoice total). | ALL UPS international shipments. Independent of country / service (Saver 65, Expedited 08, Express 07) / packaging. 21/21 runs failed. | OPEN | Build ShipmentContentsValue as MonetaryValue + CurrencyCode from the Items total; add a US→intl regression test.
F2 | P2 High | UPS Domestic | Configuration | UPS Ground rejects all 6 UPS carrier packagings: 'Service UPS 03 has no linked packages yet.' Only THB-PACKAGE + Custom pass. | No packagings are linked to UPS Ground in Settings → Shipping Catalog (a data/config gap, not code). | UPS Ground with any carrier packaging (Letter, Express Pak, Tube, Small/Medium/Large Express Box). 6/26 runs failed. | OPEN (config) | Link the intended packaging presets to UPS Ground in the Shipping Catalog.
F3 | P2 High | FedEx International | Export compliance | US→China fails on BOTH services: 'The FTR Exemption or AES Citation you provided is not valid for EEI.' | China requires an AES/EEI export filing (ITN); the default FTR exemption '-- None (using AES) --' with no ITN does not satisfy it. | FedEx international to China (both Economy & Priority). Not seen on CA/GB/AU/BR/IN at the same USD 100 value → destination-specific. | OPEN | Capture an AES ITN, or set the correct FTR exemption, for export-controlled destinations before validating.
F4 | P3 Medium | FedEx International | Validation / UX | FedEx 10kg & 25kg Boxes are REJECTED for International Economy ('Packaging type is not allowed'); allowed for Priority. | Those boxes are Priority-only FedEx packaging, but the Economy packaging dropdown still offers them, so they fail at the carrier. | FedEx International Economy + 10kg/25kg Box. Lane-independent (same on Canada & UK). 4 of the 6 FedEx-intl failures. | OPEN (UX) | Hide the intl boxes from the Economy dropdown (as the form already filters packagings elsewhere).
F5 | P2 High | UPS Domestic | Backend (RESOLVED) | Any package preset returned HTTP 500 — NoClassDefFoundError: com/multiship/backend/util/PackagingValidator$Severity — blocking all preset validation. | Stale backend build missing the PackagingValidator$Severity inner enum; the packaging-compatibility check crashed. | All preset validations (custom packages unaffected) until ~12:10 PM IST, 26 Sep. | RESOLVED | Fixed in-session by a full rebuild + restart. Add a regression test that validates a shipment with a package preset.
F6 | P3 Medium | UPS Domestic | UI consistency | UPS Ground's dropdown still offers the 6 unlinked carrier packagings (which then fail), while 3 Day Select hides its unlinked presets. | Inconsistent per-service packaging filtering; FedEx filters correctly, UPS Ground does not. | UPS Ground packaging dropdown only (cosmetic + leads to avoidable failures). | OPEN (UX) | Hide unlinked/unsupported packagings for UPS Ground, matching 3 Day Select and the FedEx behaviour.
F7 | P4 Low | FedEx Domestic | Backend (transient) | Two brief backend outages returned HTTP 502 on the validate call (~12:29 PM and ~12:59–1:01 PM); both cleared on retry. | Transient backend unavailability during testing; the toast shows the raw 'HTTP error! status: 502'. | Momentary — affected runs succeeded on retry; no lasting impact. | RESOLVED (transient) | Show a friendlier 'backend unavailable, retrying' message instead of the raw HTTP status.
Severity: P1 Critical = blocks a whole shipping path · P2 High = blocks specific services/lanes · P3 Medium = avoidable failures / UX · P4 Low = transient. 5 of 7 are open; 2 are resolved (both backend).

## Deep Dive
Per-test deep dive
1 · UPS Domestic — 26 runs · 20 pass / 6 fail · 26 Sep 2026
US→US, 4 services (Ground 03, 3 Day Select 12, 2nd Day Air 02, Next Day Air 01) × every packaging the form offered. Route MI → Los Angeles CA.
Result | 2nd Day Air & Next Day Air: all 8 packagings PASS. 3 Day Select: only THB + Custom offered, both PASS. Ground: only THB + Custom PASS.
Failures | UPS Ground rejects all 6 UPS carrier packagings — 'Service UPS 03 has no linked packages yet' (config gap F2). 6/26 runs.
Resolved defect | PackagingValidator$Severity HTTP 500 crashed all preset validation until a rebuild+restart ~12:10 PM (F5).
Notes | UI: Ground offers unlinked packagings that then fail, unlike 3 Day Select which hides them (F6). Sandbox quotes were weight-only (no rate amount).
2 · FedEx Domestic — 40 runs · 34 clean + 6 warn / 0 fail · 26 Sep 2026
US→US, 6 services (Ground, Home Delivery, Express Saver, 2Day, Standard & Priority Overnight) × every packaging offered per service.
Result | 40/40 validated — no failures. Packaging correctly filtered per service (Ground & Home Delivery are custom-only).
Warnings (6) | 'Account, service & price — 1 to review': FedEx sandbox didn't quote the exact service for the lane and listed alternatives with real USD rates. Still ships.
Nice behaviours | Home Delivery auto-ticks 'Residential'; dimensional weight applied (Tube billed 9.84 lb); FedEx sandbox returns real rate amounts.
Transient | Two HTTP 502 outages cleared on retry (F7); raw error toast could be friendlier.
3 · UPS International — 21 runs · 0 pass / 21 FAIL · 27 Sep 2026 ← TOTAL BLOCKER
US→intl, 3 UPS Worldwide services, 6 countries (AU, BR, CA, CN, FR, DE) + custom & preset packaging. Sample commercial invoice USD 100.
Result | Every single run FAILS at the live UPS carrier (Time-in-Transit) check. No UPS international label can be produced.
The defect (F1) | 'UPS Time-in-Transit rejected the request: invalid ShipmentContentsValue'. The 4 prior checks all pass; failure is identical on every country/service/package.
What worked | Intl mode (customs + commercial-invoice steps), incoterms, per-country postal validation, auto declared value, graceful error handling — everything up to the carrier call.
4 · FedEx International — 31 runs · 13 clean + 12 warn / 6 fail · 27 Sep 2026
US→intl, 2 services (Economy, Priority), 7 packagings. Canada fully swept; UK/AU/BR/CN/IN lane-tested. Sample commercial invoice USD 100.
Result | Works end-to-end on most lanes — validates and would print a label with the commercial invoice auto-included.
Packaging rule (F4) | Intl 10kg & 25kg Boxes REJECTED for Economy ('Packaging type is not allowed'); allowed for Priority. Lane-independent.
China fails (F3) | US→CN fails both services on AES/EEI export filing. Other lanes pass at the same value → China-specific.
Priority warnings | Most lanes' Priority passes with the same sandbox 'did not quote this service' rate warning; carrier still confirms valid.
Validation strength | App enforces valid state/province codes, per-country phone-digit counts (China 11 digits) and postal formats before validating.