## Summary
multiship QA retest — 2026-10-18-run3
Verdict: still not ready to release. 1 of 21 run-2 bugs fixed (R2-BUG-018), 20 still open (R2-BUG-001..017, 019..021; two with cosmetic changes), all six run-1 fixes hold, run-1 BUG-005 still open; two new bugs from the operator-role tests (R3-BUG-001 High: USER cannot list orders; R3-BUG-002 Medium: cross-tenant validate 500).
Run-2 bugs | Fixed | Still open | Still open (changed) | Cannot retest | Total
| 1 | 18 | 2 | 0 | 21
Cases | Pass | Fail | Blocked | Not run | Total
| 9 | 23 | 0 | 0 | 32
New bugs | Critical | High | Medium | Low | Total
| 0 | 1 | 1 | 0 | 2
env | Local dev test stack; carriers on sandbox hosts
base_url | http://localhost:5173
tester | Claude (Cowork) driving Claude in Chrome
session_role | ADMIN session; operator role tested with an invited USER account qa1018cop (MKL246) because the existing 'smoke' user's password is not known to QA; admin restored with the password supplied in chat (not recorded)
write_client | MKL246 only
qa_prefix | QA-1018c-
run | 3 (retest of every run-2 bug plus the run-1 fixes, and the operator role tests)
Yellow columns | Dev status / Assigned to / Developer comments / Fixed in build are for the development team to fill in.

## Retest matrix
Run-2 bug | Severity | Area | Title | Run-3 verdict | Retest case | What happened on the current build | Changed around it | Evidence | Dev status | Assigned to | Developer comments | Fixed in build
R2-BUG-001 | High | External API | External API void marks the shipment VOIDED without cancelling the label at the carrier | Still open (changed) | R3-RETEST-R2-BUG-001 | STILL OPEN (2/2 carriers). Key QA-1018c-key (id 3, MKL246, TEST, 5 scopes) issued via the UI; POST /external/shipments created 934335 (UPS P80, 1ZXXXXXXXXXXXXXXXX, 11.44) and 934336 (FedEx F77, 794893822513, 22.26). POST /external/shipments/{id}/void answered 200 'Shipment voided.' and set order+label VOIDED for both, but the Carrier API Log holds only the ship call (ids 2717 UPS, 2718 FedEx) - no cancel/void call. New on this build (not recorded in run 2): the void response now carries carrierVoided:false and the note 'Shipment voided on the platform. A carrier-side label cancellation is not wired in this environment; ensure the label is not used.' - the behaviour is unchanged, only disclosed. Key revoked afterwards; revoked token -> 401. | Void response now returns carrierVoided:false with a note that carrier-side cancellation 'is not wired in this environment' - disclosed, not fixed. | R3-KEY_revoke_dialog_QA-1018c-key.jpg
R2-BUG-002 | High | Close out / pickups | Schedule a pickup fails for every carrier: FedEx request lacks the package location, UPS pickup API answers 401, USPS/SERA request omits the contact name | Still open | R3-RETEST-R2-BUG-002 | STILL OPEN (3/3 carriers). POST /pickups: FedEx -> carrier error PACKAGELOCATION.INVALID (request body still has no packageLocation); UPS -> 401 code 250002 from the UPS pickup API; USPS/SERA -> error 4522242 contact name missing (request has no name field). Same three failures as run 2.
R2-BUG-003 | High | Close out / pickups | Close whole day fails with a server 500 (no carrier call) and the open-labels query still fails for today | Still open | R3-RETEST-R2-BUG-003 | STILL OPEN. GET /manifests/open?carrierCode=FEDEX&closeDate=2026-10-18 -> 500; same for UPS -> 500; POST /manifests/close-day -> 500 with no carrier call in the Carrier API Log. Unchanged from run 2 (close-out of other days not retried, per the earlier decision).
R2-BUG-004 | High | Data integrity | Per-box declared values are ignored on multi-box shipments (run-1 BUG-007 still present) | Still open | R3-RETEST-R2-BUG-004 | STILL OPEN (2/2). Two-box purchases with packages declared 50 / 150: 934329 (UPS) and 934330 (FedEx) - the carrier requests in the Carrier API Log again carry 100 / 100 (total split evenly) instead of 50 / 150.
R2-BUG-005 | High | Data integrity | Duplicate label purchases are accepted on the internal purchase endpoint and on the External API (run-1 BUG-006, now confirmed on the integration path) | Still open | R3-RETEST-R2-BUG-005 | STILL OPEN (2/2 paths). POST /orders/manual-label twice with reference QA-1018c-D001 -> 934331 and 934332 both 200 with labels; POST /external/shipments twice with reference QA-1018c-EXT1 -> 934335 and 934337 both 201. No idempotency key, no refusal, no warning on either path.
R2-BUG-006 | Medium | Bulk Mailer | Bulk import template and Errors (CSV) use carrier service codes the importer rejects (run-1 BUG-014 still present) | Still open (changed) | R3-RETEST-R2-BUG-006 | STILL OPEN (2/2). The template downloaded from /orders/import/template-client.csv still carries SHIPVIA_CD FEDEX_GROUND; uploaded for MKL246 (upload 24) it fails with "Service 'FEDEX_GROUND' is not mapped for MKL246 - it is a FEDEX service code, but a file import must use a Shipping Service Mapping rule". Errors (CSV) (QA-1018c-template-errors.csv) is again written in the internal layout (orderRef, clientCode, ... serviceType, errors) and re-uploading it (upload 25) fails on the same rule. Mitigation seen on this build: the validate step shows a 'Ship via codes for MKL246' panel listing the valid codes (F77 FedEx Ground, P80 UPS Ground), and a 'Save all, including errors' button - the template itself is still wrong. | Validate step now shows a 'Ship via codes for MKL246' help panel (F77, P80) and a 'Save all, including errors' button; the template itself still ships FEDEX_GROUND. | R3-R2-BUG-006_errors_csv_reupload_still_unmapped.jpg
R2-BUG-007 | Medium | Data integrity | Carrier API Log rows from bulk label runs carry no order number (run-1 BUG-015 still present) | Still open | R3-RETEST-R2-BUG-007 | STILL OPEN (2/2). Import #13 (QA-1018c-bulk2.csv, label batch 34): Generate labels created 934339 (FedEx 794893822638) and 934338 (UPS) in about 30 s, both GENERATED. Carrier API Log rows 2720 (UPS) and 2721 (FedEx) have orderNo null; GET /admin/carrier-api-log?orderNo=934338 and ?orderNo=934339 return nothing. |  | R3-R2-BUG-007_import13_complete_934338_934339.jpg
R2-BUG-008 | Medium | Settings | A custom field marked 'Required on new shipments' is not enforced | Still open | R3-RETEST-R2-BUG-008 | STILL OPEN (2/2). Definition qa_1018c_dept 'QA-1018c Department' (TEXT, Required, Active, position 110) saved for MKL246 and shown on the New Shipment form as 'QA-1018C DEPARTMENT *'. With the field left empty, Validate reported 'All checks passed - ready to generate the label' and Generate bought FedEx Ground label 794893824160 (order 934340, customFields {}); the UI purchase request carried no customFields at all. POST /shipments/validate without custom fields also answers overall PASS. Definition deleted afterwards ('Definition deleted'). |  | R3-R2-BUG-008_required_custom_field_definition.jpg, R3-R2-BUG-008_all_checks_passed_with_empty_required_field.jpg, R3-R2-BUG-008_label_934340_generated.jpg
R2-BUG-009 | Medium | Validation | Server accepts unusable phone numbers, bad emails and over-long fields that the form rejects (run-1 BUG-003/BUG-004 still present, also on the External API) | Still open | R3-RETEST-R2-BUG-009 | STILL OPEN (2/2). POST /shipments/validate with recipient.phone 'abc', email 'not-an-email', 120-char name, 300-char address and 300-char reference still passes (overall PASS, no local errors); the form rejects the same values client-side only.
R2-BUG-010 | Medium | Settings | Deleting a warehouse that is attached to clients and used by orders needs only a single confirm | Still open | R3-RETEST-R2-BUG-010 | STILL OPEN (2/2 dialog opens, cancelled both times). Settings > Warehouses > 3PL-EAST (Platform, attached to 3 clients, origin of the MKL246 orders) > Row actions > Delete opens 'Delete warehouse 3PL-EAST? It is currently attached to 3 clients - they will be unlinked.' with Cancel / Delete - one click away, no type-to-confirm, no mention of the orders that reference it, no block while attached. Cancelled; the warehouse is intact (2 of 2 warehouses listed, Active). |  | R3-R2-BUG-010_delete_warehouse_single_confirm.jpg
R2-BUG-011 | Medium | Validation | No sanctions/embargo check of its own: shipments to CU, KP, IR are only stopped by the carriers (USPS validate passes for Iran) | Still open | R3-RETEST-R2-BUG-011 | STILL OPEN (2/2). USPS validate to Iran (IR) answers overall WARN with no sanctions/embargo error; the app relies on the carrier to refuse.
R2-BUG-012 | Medium | Orders grid | Tab badges and Failed queue miss legacy FAILED-label orders; All badge 8 short of the list (run-1 BUG-013 still present) | Still open | R3-RETEST-R2-BUG-012 | STILL OPEN (2/2). /orders/stats buckets sum to 34,004 while the unfiltered list total is 34,014 (10 orders in no bucket, was 8 in run 2 - the gap grows with new voided/failed rows); legacy order 900001 (label FAILED) still missing from the Error filter.
R2-BUG-013 | Medium | Orders grid | Export CSV writes only the current page of a filtered result set | Still open | R3-RETEST-R2-BUG-013 | STILL OPEN (2/2). Search QA-1018c matches 11 orders (API totalElements 11). Export at 10/page -> orders-2026-10-18T10-27-47-669Z.csv with 10 data rows; after switching to 100/page -> 11 rows. Export still writes the current page only, with no warning or 'current page' label.
R2-BUG-014 | Low | Label output | Label page preview shows the platform default ship-from (Bengaluru) instead of the order's sender (run-1 BUG-001 still present) | Still open | R3-RETEST-R2-BUG-014 | STILL OPEN (2/2). View Label for 934333 (UPS) and 934339 (FedEx) still renders SHIP FROM 'Multiship Warehouse, 1 Warehouse Way, Bengaluru, KA 560001' while the order details dialog and the carrier requests (Carrier API Log 2708 UPS Shipper 'MKL', 2721 FedEx shipper 'Central Warehouse', both 8191 Logistics Dr, Zeeland MI 49464) carry the real sender. Preview only; the carrier label is correct. |  | R3-R2-BUG-014_label_preview_934333_bengaluru_shipfrom.jpg, R3-R2-BUG-014_label_preview_934339_bengaluru_shipfrom.jpg
R2-BUG-015 | Low | Void / reissue | USPS void fails with a raw non-unique-result error when the sandbox tracking number is shared (run-1 BUG-010 still present); UPS void rejection returns HTTP 200 | Still open | R3-RETEST-R2-BUG-015 | STILL OPEN (2/2). UPS void of a sandbox label -> HTTP 200 with message 'rejected ... No shipment found within the allowed void period' (success code for a failure); USPS void -> 502 'Query did not return a unique result' because sandbox labels share tracking 9400111969000940000011.
R2-BUG-016 | Low | Void / reissue | Reissuing a voided label warns that the reference was 'already shipped' on the same order | Still open | R3-RETEST-R2-BUG-016 | STILL OPEN (2/2). Void of 934339 (FedEx 794893822638) from the grid: dialog 'Void order #934339? This cancels the label at the carrier - it cannot be undone', toast 'Order 934339: 1 batch(es) voided', Carrier API Log 2722 apis-sandbox.fedex.com/ship/v1/shipments/cancel (internal void still cancels at the carrier). Reissue label opened the form pre-filled ('Reissuing label for order #934339'); Validate shows 'Reference QA-1018c-BM-1 already shipped on order #934339 (2026-10-18). Make sure this isn't a second shipment of the same order.' - the warning names the order being reissued, and calls a voided label 'shipped'. Regenerate worked: new tracking 794893823895, page shows 'Previous label: 794893822638 (voided 4:01:48 PM, reissued 4:02:52 PM)'. Side observations: the reissue form of a bulk-imported order has empty, required Length/Width/Height (bulk rows carry no dimensions) so Validate is blocked until they are typed; the Ship from dropdown again reads 'Manual sender' for a warehouse-origin order; the preview again shows the Bengaluru ship-from (R2-BUG-014). |  | R3-VOID_dialog_934339.jpg, R3-R2-BUG-016_reissue_duplicate_warning_same_order_934339.jpg, R3-R2-BUG-016_reissued_label_934339.jpg
R2-BUG-017 | Low | Returns | 'Return of #' does not load the original recipient into the Return from block | Still open | R3-RETEST-R2-BUG-017 | STILL OPEN (2/2). New return, client MKL246, 'Return of #' 934333 (scripted) and 934338 (typed, Tab out): the 'Return from - customer' block stays empty (Full name, Address, City, Phone, Email all blank) and no request for the order is made (no GET /orders/9343xx in the resource timeline). The block must be typed by hand. New on this build: a banner 'Customer email required for return labels ... UPS rejects the label with 9120145' appears once a client is chosen. |  | R3-R2-BUG-017_return_of_934333_top.jpg, R3-R2-BUG-017_return_from_block_empty_after_934338.jpg
R2-BUG-018 | Low | Orders grid | Reversed date range shows an empty grid without a message (run-1 BUG-020 still present) | Fixed | R3-RETEST-R2-BUG-018 | FIXED on this build (2/2). Setting From 18-10-2026 / To 01-10-2026 (and again 12-10 / 05-10 after Clear) shows an inline badge 'From date is after To date' beside the date pickers and 'Nothing matches the current filters.' in the grid. Residual: the API itself still answers GET /orders?createdFrom=2026-10-18&createdTo=2026-10-01 with 200 and an empty page rather than a 400 (minor, API hygiene). |  | R3-R2-BUG-018_reversed_dates_now_flagged.jpg
R2-BUG-019 | Low | Security | Issue API key dialog defaults to All clients, LIVE and all 7 scopes | Still open | R3-RETEST-R2-BUG-019 | STILL OPEN (2/2 dialog opens). Settings > API keys > Issue API key still opens with All clients, LIVE and 7/7 scopes preselected (screenshot). One client / TEST / 5 scopes had to be chosen by hand for the QA key. |  | R3-R2-BUG-019_issue_api_key_dialog_defaults.jpg
R2-BUG-020 | Medium | Options | Shipment Check quote omits signature and declared-value surcharges (run-1 BUG-008 still present) | Still open | R3-RETEST-R2-BUG-020 | STILL OPEN (2/2). UPS Ground (service 03) with ADULT signature on order 934333: the Validate quote is 11.33 (plain Ground rate) while the UPS ship response (Carrier API Log 2708, PackageServiceOptions.DeliveryConfirmation DCISType 3, DeclaredValue 80) bills TotalCharges 20.79 - the signature and declared-value surcharges are missing from the Shipment Check quote.
R2-BUG-021 | Low | Options | Insured value is never sent to the carrier (run-1 BUG-009 still present) | Still open | R3-RETEST-R2-BUG-021 | STILL OPEN (2/2). UPS Ground purchase with options.insuredValue 500 (order 934334): the UPS ship request in the Carrier API Log carries no InsuredValue/insurance element (only the declared-value element), so no insurance is bought; label cost equals the uninsured rate.

## Run-1 fixes
Run-1 bug | Title | Run-3 check | Case | Detail
BUG-002 | Reason of export defaults to 'Sample' on every international shipment because every MKL246/THB000 carrier account carries shippingPurpose=SAMPLE; the form copies the account default when the field is empty | Fix holds | R3-FIX-BUG-002 | FIX HOLDS. New Shipment for MKL246 with recipient country Canada: 'Reason of export' shows '-- Select --' (9 options), Incoterms '-- Select --', FTR exemption '-- None (using AES) --'; nothing is preselected. Same on the Return form.
BUG-011 | Return form pre-fills the customer ('Return from') block with the merchant's own address and phone, and 'Return of #' does not load the original recipient | Fix holds | R3-FIX-BUG-011 | FIX HOLDS. The 'Return from - customer' block starts empty; the 'Return to - your address' block fills from the MKL246 client record (MKL, 8191 Logistics Dr, Zeeland MI 49464) once the client is chosen.
BUG-012 | 'Shipment vs return' filter is silently broken: it does nothing on its own, then stays applied invisibly and survives 'Clear all' | Fix holds | R3-FIX-BUG-012 | FIX HOLDS. Filters > Shipment vs return = Returns only refetches at once (18 lines, 1 of 1, badge 'Filters 1'); Clear all resets the select to Any and the grid to 100 lines / 1 of 341.
BUG-016 | 'Generate labels' on an import purchases labels for every row with a single click and no confirmation | Fix holds | R3-FIX-BUG-016 | FIX HOLDS. Import #13 > Generate labels opens 'Generate labels for 2 rows? This buys real labels from the carrier and can't be undone.' with Not now / Generate labels (screenshot).
BUG-018 | Add funds: the Add button stays enabled on an account that is not authorized with Stamps.com, and any amount is allowed when the balance is unknown | Fix holds | R3-FIX-BUG-018 | FIX HOLDS. Account 874157 (balance $158.53, 'Can add up to $9,841.47'): 9841.47 accepted (button 'Add $9,841.47', new balance $10,000.00); 9841.48 refused with 'That would go over Stamps.com's $10,000.00 balance limit. You can add up to $9,841.47.'; 9.99 and 'abc' leave the button as a disabled 'Add funds'; 10 accepted (new balance $168.53). Account 5 (USPS-STAMP TEST, 'Check failed', never used) no longer offers an Add funds control at all. Recent top-ups still lists the two Failed $25.00 attempts from run 2; nothing was submitted in run 3; balance unchanged.
BUG-019 | Add funds rejects the exact maximum amount it advertises (9841.47) with a wrong 'dollars and cents' message | Fix holds | R3-FIX-BUG-018 | FIX HOLDS. Account 874157 (balance $158.53, 'Can add up to $9,841.47'): 9841.47 accepted (button 'Add $9,841.47', new balance $10,000.00); 9841.48 refused with 'That would go over Stamps.com's $10,000.00 balance limit. You can add up to $9,841.47.'; 9.99 and 'abc' leave the button as a disabled 'Add funds'; 10 accepted (new balance $168.53). Account 5 (USPS-STAMP TEST, 'Check failed', never used) no longer offers an Add funds control at all. Recent top-ups still lists the two Failed $25.00 attempts from run 2; nothing was submitted in run 3; balance unchanged.
BUG-005 | Label purchase trusts the request's carrierCode over the selected account, so a mismatch calls the wrong carrier and saves an ERROR order | Still open (changed) | R3-RETEST-BUG-005 | STILL OPEN (2/2). UPS Ground body on account 2 (THB-UPS) with carrierCode FEDEX: POST /orders/manual-label -> 502 'The carrier rejected the shipment: FedEx rejected the credentials (NOT.AUTHORIZED.ERROR). Confirm the Client ID / Secret are FedEx OAuth keys...' and ERROR orders 934341 and 934342 are saved (refs QA-1018c-QA-1018c-MM1 / -MM3), Carrier API Log 2739 apis-sandbox.fedex.com/oauth/token 401 - the server still routes by the body's carrierCode and calls FedEx with a UPS account. Change since run 1: Validate no longer passes the FEDEX mismatch (overall FAIL with the same credentials text), and carrierCode FOO is now refused by the purchase endpoint with 400 'Unsupported carrier: FOO' and no order (Validate still passes it with a WEIGHT_ONLY quote).
BUG-001 | Label screen shows a fallback preview with the wrong Ship-From (Bengaluru default) and order number as REF when preview.png returns 503 | Still open | see R2-BUG-014 | carried as R2-BUG-014
BUG-003 | Server accepts unusable phone numbers and emails that the New Shipment form rejects (API/validation gap) | Still open | see R2-BUG-009 | carried as R2-BUG-009
BUG-004 | Validate says 'ready to ship' for over-long name, address and reference, then UPS rejects the label and an ERROR order is created | Still open | see R2-BUG-009 | carried as R2-BUG-009
BUG-006 | Label purchase endpoint accepts a second label for the same reference and for simultaneous requests; the duplicate check exists only as a Validate warning | Still open | see R2-BUG-005 | carried as R2-BUG-005
BUG-007 | Per-box declared values are ignored: the carrier gets box 1's value split evenly across all boxes | Still open | see R2-BUG-004 | carried as R2-BUG-004
BUG-008 | Shipment Check price leaves out signature and declared-value charges, so the label costs far more than the quote | Still open | see R2-BUG-020 | carried as R2-BUG-020
BUG-009 | 'Insured value' is never sent to any carrier and the server does not enforce the form's insured <= declared rule | Still open | see R2-BUG-021 | carried as R2-BUG-021
BUG-010 | USPS void shows a raw database error when the tracking number matches many labels, and looks labels up by tracking number instead of order or label id | Still open | see R2-BUG-015 | carried as R2-BUG-015
BUG-013 | Five failed orders (label status FAILED) are invisible in the Failed tab and Error filter, and the All orders badge (33,949) disagrees with the list total (33,957) | Still open | see R2-BUG-012 | carried as R2-BUG-012
BUG-014 | Bulk import template and Errors (CSV) export both use carrier service codes that the importer itself rejects, so the documented fix-and-re-upload loop cannot work | Still open (changed) | see R2-BUG-006 | carried as R2-BUG-006
BUG-015 | Carrier API Log entries written by bulk label runs have no order number, so bulk labels cannot be traced from the log | Still open | see R2-BUG-007 | carried as R2-BUG-007
BUG-017 | Close out day cannot list today's open labels: GET /manifests/open returns 500 for busy dates, so the dialog falls back to 'type the numbers' | Still open | see R2-BUG-003 | carried as R2-BUG-003
BUG-020 | A reversed date range (From after To) silently shows an empty grid instead of a message | Fixed | see R2-BUG-018 | carried as R2-BUG-018

## Test cases
ID | Area | Priority | Kind | Title | Role | Client | Method | Expected | Result | Actual / notes | Bugs | Evidence | Timestamp (UTC) | Dev status | Assigned to | Developer comments | Fixed in build
R3-FIX-BUG-002 | International | P2 | retest | Regression check of run-1 fix BUG-002: Reason for export has no silent default | ADMIN | MKL246 | UI (New Return / New Shipment forms) | No preselected reason | PASS | FIX HOLDS. New Shipment for MKL246 with recipient country Canada: 'Reason of export' shows '-- Select --' (9 options), Incoterms '-- Select --', FTR exemption '-- None (using AES) --'; nothing is preselected. Same on the Return form. |  |  | 2026-10-18T10:35:25Z
R3-FIX-BUG-011 | Returns | P2 | retest | Regression check of run-1 fix BUG-011: Return from block is not pre-filled with the wrong party | ADMIN | MKL246 | UI (New Return / New Shipment forms) | Customer block empty or correct; return-to = client return address | PASS | FIX HOLDS. The 'Return from - customer' block starts empty; the 'Return to - your address' block fills from the MKL246 client record (MKL, 8191 Logistics Dr, Zeeland MI 49464) once the client is chosen. |  | R3-R2-BUG-017_return_from_block_empty_after_934338.jpg | 2026-10-18T10:35:25Z
R3-FIX-BUG-012 | Orders grid | P1 | retest | Regression check of run-1 fix BUG-012: 'Shipment vs return' filter refetches and Clear all resets | ADMIN | MKL246 | UI (orders grid, Blob captured in page) + API | Filter applies immediately; Clear all resets | PASS | FIX HOLDS. Filters > Shipment vs return = Returns only refetches at once (18 lines, 1 of 1, badge 'Filters 1'); Clear all resets the select to Any and the grid to 100 lines / 1 of 341. |  |  | 2026-10-18T10:29:30Z
R3-FIX-BUG-016 | Bulk Mailer | P1 | retest | Regression check of run-1 fix BUG-016: Generate labels asks for confirmation | ADMIN | MKL246 | UI (Bulk Mailer) + API | Confirmation before buying | PASS | FIX HOLDS. Import #13 > Generate labels opens 'Generate labels for 2 rows? This buys real labels from the carrier and can't be undone.' with Not now / Generate labels (screenshot). |  | R3-FIX-BUG-016_bulk_generate_confirm_dialog.jpg | 2026-10-18T10:27:33Z
R3-FIX-BUG-018 | Funds | P1 | retest | Regression check of run-1 fixes BUG-018/BUG-019: Add Funds limits and unauthorized account | ADMIN | MKL246 | UI (Carrier Accounts > Add postage funds), not submitted | Exact maximum accepted; over-limit refused; unauthorized account cannot add funds | PASS | FIX HOLDS. Account 874157 (balance $158.53, 'Can add up to $9,841.47'): 9841.47 accepted (button 'Add $9,841.47', new balance $10,000.00); 9841.48 refused with 'That would go over Stamps.com's $10,000.00 balance limit. You can add up to $9,841.47.'; 9.99 and 'abc' leave the button as a disabled 'Add funds'; 10 accepted (new balance $168.53). Account 5 (USPS-STAMP TEST, 'Check failed', never used) no longer offers an Add funds control at all. Recent top-ups still lists the two Failed $25.00 attempts from run 2; nothing was submitted in run 3; balance unchanged. |  | R3-FIX-BUG-018_add_funds_over_limit_message.jpg | 2026-10-18T10:39:36Z
R3-RETEST-BUG-005 | Label purchase (API) | P3 | retest | Retest run-1 BUG-005: carrierCode in the body disagrees with the selected account | ADMIN | MKL246 | API replay of POST /api/v1/orders/manual-label and /shipments/validate | 400 'carrierCode does not match the carrier account', no order, no carrier call | FAIL | STILL OPEN (2/2). UPS Ground body on account 2 (THB-UPS) with carrierCode FEDEX: POST /orders/manual-label -> 502 'The carrier rejected the shipment: FedEx rejected the credentials (NOT.AUTHORIZED.ERROR). Confirm the Client ID / Secret are FedEx OAuth keys...' and ERROR orders 934341 and 934342 are saved (refs QA-1018c-QA-1018c-MM1 / -MM3), Carrier API Log 2739 apis-sandbox.fedex.com/oauth/token 401 - the server still routes by the body's carrierCode and calls FedEx with a UPS account. Change since run 1: Validate no longer passes the FEDEX mismatch (overall FAIL with the same credentials text), and carrierCode FOO is now refused by the purchase endpoint with 400 'Unsupported carrier: FOO' and no order (Validate still passes it with a WEIGHT_ONLY quote). |  |  | 2026-10-18T10:40:25Z
R3-RETEST-R2-BUG-001 | External API | P1 | retest | Retest R2-BUG-001: External API void must cancel the label at the carrier | ADMIN | MKL246 | UI (issue/revoke key) + External API with X-API-Key + Carrier API Log | Carrier cancel endpoint called before the shipment is marked VOIDED, as the internal void does | FAIL | STILL OPEN (2/2 carriers). Key QA-1018c-key (id 3, MKL246, TEST, 5 scopes) issued via the UI; POST /external/shipments created 934335 (UPS P80, 1ZXXXXXXXXXXXXXXXX, 11.44) and 934336 (FedEx F77, 794893822513, 22.26). POST /external/shipments/{id}/void answered 200 'Shipment voided.' and set order+label VOIDED for both, but the Carrier API Log holds only the ship call (ids 2717 UPS, 2718 FedEx) - no cancel/void call. New on this build (not recorded in run 2): the void response now carries carrierVoided:false and the note 'Shipment voided on the platform. A carrier-side label cancellation is not wired in this environment; ensure the label is not used.' - the behaviour is unchanged, only disclosed. Key revoked afterwards; revoked token -> 401. |  | R3-KEY_revoke_dialog_QA-1018c-key.jpg | 2026-10-18T10:24:45Z
R3-RETEST-R2-BUG-002 | Close out / pickups | P1 | retest | Retest R2-BUG-002: Schedule a pickup on FedEx, UPS and USPS | ADMIN | MKL246 | API + Carrier API Log | Pickup confirmation number from each sandbox | FAIL | STILL OPEN (3/3 carriers). POST /pickups: FedEx -> carrier error PACKAGELOCATION.INVALID (request body still has no packageLocation); UPS -> 401 code 250002 from the UPS pickup API; USPS/SERA -> error 4522242 contact name missing (request has no name field). Same three failures as run 2. |  |  | 2026-10-18T10:24:31Z
R3-RETEST-R2-BUG-003 | Close out / pickups | P1 | retest | Retest R2-BUG-003: Close whole day and the open-labels query | ADMIN | MKL246 | API | Open labels listed and the day closed at the carrier | FAIL | STILL OPEN. GET /manifests/open?carrierCode=FEDEX&closeDate=2026-10-18 -> 500; same for UPS -> 500; POST /manifests/close-day -> 500 with no carrier call in the Carrier API Log. Unchanged from run 2 (close-out of other days not retried, per the earlier decision). |  |  | 2026-10-18T10:24:31Z
R3-RETEST-R2-BUG-004 | Data integrity | P1 | retest | Retest R2-BUG-004: per-box declared values on multi-box shipments | ADMIN | MKL246 | API + Carrier API Log | Each package carries its own declared value | FAIL | STILL OPEN (2/2). Two-box purchases with packages declared 50 / 150: 934329 (UPS) and 934330 (FedEx) - the carrier requests in the Carrier API Log again carry 100 / 100 (total split evenly) instead of 50 / 150. |  |  | 2026-10-18T10:24:31Z
R3-RETEST-R2-BUG-005 | Data integrity | P1 | retest | Retest R2-BUG-005: duplicate label purchases (internal endpoint and External API) | ADMIN | MKL246 | API + External API | Second purchase refused or requires an explicit override | FAIL | STILL OPEN (2/2 paths). POST /orders/manual-label twice with reference QA-1018c-D001 -> 934331 and 934332 both 200 with labels; POST /external/shipments twice with reference QA-1018c-EXT1 -> 934335 and 934337 both 201. No idempotency key, no refusal, no warning on either path. |  |  | 2026-10-18T10:24:31Z
R3-RETEST-R2-BUG-006 | Bulk Mailer | P2 | retest | Retest R2-BUG-006: shipped template row and Errors (CSV) round trip | ADMIN | MKL246 | UI (Bulk Mailer) + API | Template validates; Errors (CSV) round-trips | FAIL | STILL OPEN (2/2). The template downloaded from /orders/import/template-client.csv still carries SHIPVIA_CD FEDEX_GROUND; uploaded for MKL246 (upload 24) it fails with "Service 'FEDEX_GROUND' is not mapped for MKL246 - it is a FEDEX service code, but a file import must use a Shipping Service Mapping rule". Errors (CSV) (QA-1018c-template-errors.csv) is again written in the internal layout (orderRef, clientCode, ... serviceType, errors) and re-uploading it (upload 25) fails on the same rule. Mitigation seen on this build: the validate step shows a 'Ship via codes for MKL246' panel listing the valid codes (F77 FedEx Ground, P80 UPS Ground), and a 'Save all, including errors' button - the template itself is still wrong. |  | R3-R2-BUG-006_errors_csv_reupload_still_unmapped.jpg | 2026-10-18T10:27:33Z
R3-RETEST-R2-BUG-007 | Data integrity | P2 | retest | Retest R2-BUG-007: Carrier API Log rows from a bulk label run carry the order number | ADMIN | MKL246 | UI (Bulk Mailer) + API | Log rows linked to 934338 / 934339 | FAIL | STILL OPEN (2/2). Import #13 (QA-1018c-bulk2.csv, label batch 34): Generate labels created 934339 (FedEx 794893822638) and 934338 (UPS) in about 30 s, both GENERATED. Carrier API Log rows 2720 (UPS) and 2721 (FedEx) have orderNo null; GET /admin/carrier-api-log?orderNo=934338 and ?orderNo=934339 return nothing. |  | R3-R2-BUG-007_import13_complete_934338_934339.jpg | 2026-10-18T10:27:33Z
R3-RETEST-R2-BUG-008 | Settings | P2 | retest | Retest R2-BUG-008: a custom field marked 'Required on new shipments' is enforced | ADMIN | MKL246 | UI (Settings > Custom Fields, New Shipment) + API | Validate blocks with a message naming the field | FAIL | STILL OPEN (2/2). Definition qa_1018c_dept 'QA-1018c Department' (TEXT, Required, Active, position 110) saved for MKL246 and shown on the New Shipment form as 'QA-1018C DEPARTMENT *'. With the field left empty, Validate reported 'All checks passed - ready to generate the label' and Generate bought FedEx Ground label 794893824160 (order 934340, customFields {}); the UI purchase request carried no customFields at all. POST /shipments/validate without custom fields also answers overall PASS. Definition deleted afterwards ('Definition deleted'). |  | R3-R2-BUG-008_required_custom_field_definition.jpg, R3-R2-BUG-008_all_checks_passed_with_empty_required_field.jpg, R3-R2-BUG-008_label_934340_generated.jpg | 2026-10-18T10:37:44Z
R3-RETEST-R2-BUG-009 | Validation | P1 | retest | Retest R2-BUG-009: server-side contact and length validation | ADMIN | MKL246 | API replay of POST /api/v1/shipments/validate | Same rules as the UI, enforced on the server | FAIL | STILL OPEN (2/2). POST /shipments/validate with recipient.phone 'abc', email 'not-an-email', 120-char name, 300-char address and 300-char reference still passes (overall PASS, no local errors); the form rejects the same values client-side only. |  |  | 2026-10-18T10:24:31Z
R3-RETEST-R2-BUG-010 | Settings | P2 | retest | Retest R2-BUG-010: deleting a warehouse in use needs more than a single confirm | ADMIN | MKL246 | UI (Settings > Warehouses), dialog cancelled | Blocked while attached, or a strong confirmation naming the impact | FAIL | STILL OPEN (2/2 dialog opens, cancelled both times). Settings > Warehouses > 3PL-EAST (Platform, attached to 3 clients, origin of the MKL246 orders) > Row actions > Delete opens 'Delete warehouse 3PL-EAST? It is currently attached to 3 clients - they will be unlinked.' with Cancel / Delete - one click away, no type-to-confirm, no mention of the orders that reference it, no block while attached. Cancelled; the warehouse is intact (2 of 2 warehouses listed, Active). |  | R3-R2-BUG-010_delete_warehouse_single_confirm.jpg | 2026-10-18T10:38:24Z
R3-RETEST-R2-BUG-011 | Validation | P2 | retest | Retest R2-BUG-011: embargoed destinations (IR) pass validation | ADMIN | MKL246 | API | Shipment to an embargoed country refused by the app | FAIL | STILL OPEN (2/2). USPS validate to Iran (IR) answers overall WARN with no sanctions/embargo error; the app relies on the carrier to refuse. |  |  | 2026-10-18T10:24:31Z
R3-RETEST-R2-BUG-012 | Orders grid | P2 | retest | Retest R2-BUG-012: status buckets vs list total; legacy FAILED-label orders | ADMIN | MKL246 | API + UI | Badges and queue tabs account for every order | FAIL | STILL OPEN (2/2). /orders/stats buckets sum to 34,004 while the unfiltered list total is 34,014 (10 orders in no bucket, was 8 in run 2 - the gap grows with new voided/failed rows); legacy order 900001 (label FAILED) still missing from the Error filter. |  |  | 2026-10-18T10:24:31Z
R3-RETEST-R2-BUG-013 | Orders grid | P2 | retest | Retest R2-BUG-013: Export CSV writes the whole filtered result set | ADMIN | MKL246 | UI (orders grid, Blob captured in page) + API | All matching rows, or a clear current-page label | FAIL | STILL OPEN (2/2). Search QA-1018c matches 11 orders (API totalElements 11). Export at 10/page -> orders-2026-10-18T10-27-47-669Z.csv with 10 data rows; after switching to 100/page -> 11 rows. Export still writes the current page only, with no warning or 'current page' label. |  |  | 2026-10-18T10:29:30Z
R3-RETEST-R2-BUG-014 | Label output | P3 | retest | Retest R2-BUG-014: label page preview shows the order's sender | ADMIN | MKL246 | UI (View Label page) + Carrier API Log | Preview shows the order's ship-from (MKL, Zeeland MI) | FAIL | STILL OPEN (2/2). View Label for 934333 (UPS) and 934339 (FedEx) still renders SHIP FROM 'Multiship Warehouse, 1 Warehouse Way, Bengaluru, KA 560001' while the order details dialog and the carrier requests (Carrier API Log 2708 UPS Shipper 'MKL', 2721 FedEx shipper 'Central Warehouse', both 8191 Logistics Dr, Zeeland MI 49464) carry the real sender. Preview only; the carrier label is correct. |  | R3-R2-BUG-014_label_preview_934333_bengaluru_shipfrom.jpg, R3-R2-BUG-014_label_preview_934339_bengaluru_shipfrom.jpg | 2026-10-18T10:31:30Z
R3-RETEST-R2-BUG-015 | Void / reissue | P2 | retest | Retest R2-BUG-015: UPS void rejection and USPS non-unique void | ADMIN | MKL246 | API | Failure status code for a rejected void; USPS void keyed by order, not tracking | FAIL | STILL OPEN (2/2). UPS void of a sandbox label -> HTTP 200 with message 'rejected ... No shipment found within the allowed void period' (success code for a failure); USPS void -> 502 'Query did not return a unique result' because sandbox labels share tracking 9400111969000940000011. |  |  | 2026-10-18T10:24:31Z
R3-RETEST-R2-BUG-016 | Void / reissue | P3 | retest | Retest R2-BUG-016: reissuing a voided label warns 'already shipped' on the same order | ADMIN | MKL246 | UI (grid void, Reissue label form) + Carrier API Log | No duplicate warning for the order being reissued | FAIL | STILL OPEN (2/2). Void of 934339 (FedEx 794893822638) from the grid: dialog 'Void order #934339? This cancels the label at the carrier - it cannot be undone', toast 'Order 934339: 1 batch(es) voided', Carrier API Log 2722 apis-sandbox.fedex.com/ship/v1/shipments/cancel (internal void still cancels at the carrier). Reissue label opened the form pre-filled ('Reissuing label for order #934339'); Validate shows 'Reference QA-1018c-BM-1 already shipped on order #934339 (2026-10-18). Make sure this isn't a second shipment of the same order.' - the warning names the order being reissued, and calls a voided label 'shipped'. Regenerate worked: new tracking 794893823895, page shows 'Previous label: 794893822638 (voided 4:01:48 PM, reissued 4:02:52 PM)'. Side observations: the reissue form of a bulk-imported order has empty, required Length/Width/Height (bulk rows carry no dimensions) so Validate is blocked until they are typed; the Ship from dropdown again reads 'Manual sender' for a warehouse-origin order; the preview again shows the Bengaluru ship-from (R2-BUG-014). |  | R3-VOID_dialog_934339.jpg, R3-R2-BUG-016_reissue_duplicate_warning_same_order_934339.jpg, R3-R2-BUG-016_reissued_label_934339.jpg | 2026-10-18T10:33:29Z
R3-RETEST-R2-BUG-017 | Returns | P3 | retest | Retest R2-BUG-017: 'Return of #' loads the original recipient into the Return from block | ADMIN | MKL246 | UI (New Return / New Shipment forms) | Customer block prefilled from the original order | FAIL | STILL OPEN (2/2). New return, client MKL246, 'Return of #' 934333 (scripted) and 934338 (typed, Tab out): the 'Return from - customer' block stays empty (Full name, Address, City, Phone, Email all blank) and no request for the order is made (no GET /orders/9343xx in the resource timeline). The block must be typed by hand. New on this build: a banner 'Customer email required for return labels ... UPS rejects the label with 9120145' appears once a client is chosen. |  | R3-R2-BUG-017_return_of_934333_top.jpg, R3-R2-BUG-017_return_from_block_empty_after_934338.jpg | 2026-10-18T10:35:25Z
R3-RETEST-R2-BUG-018 | Orders grid | P3 | retest | Retest R2-BUG-018: reversed date range | ADMIN | MKL246 | API + UI | Validation message, or the range auto-corrected | PASS | FIXED on this build (2/2). Setting From 18-10-2026 / To 01-10-2026 (and again 12-10 / 05-10 after Clear) shows an inline badge 'From date is after To date' beside the date pickers and 'Nothing matches the current filters.' in the grid. Residual: the API itself still answers GET /orders?createdFrom=2026-10-18&createdTo=2026-10-01 with 200 and an empty page rather than a 400 (minor, API hygiene). |  | R3-R2-BUG-018_reversed_dates_now_flagged.jpg | 2026-10-18T10:29:30Z
R3-RETEST-R2-BUG-019 | Security | P3 | retest | Retest R2-BUG-019: Issue API key dialog defaults | ADMIN | MKL246 | UI | Least-privilege defaults (One client, TEST, minimal scopes) | FAIL | STILL OPEN (2/2 dialog opens). Settings > API keys > Issue API key still opens with All clients, LIVE and 7/7 scopes preselected (screenshot). One client / TEST / 5 scopes had to be chosen by hand for the QA key. |  | R3-R2-BUG-019_issue_api_key_dialog_defaults.jpg | 2026-10-18T10:24:45Z
R3-RETEST-R2-BUG-020 | Options | P2 | retest | Retest R2-BUG-020: Shipment Check quote omits surcharges | ADMIN | MKL246 | API + Carrier API Log | Quote includes the signature surcharge | FAIL | STILL OPEN (2/2). UPS Ground (service 03) with ADULT signature on order 934333: the Validate quote is 11.33 (plain Ground rate) while the UPS ship response (Carrier API Log 2708, PackageServiceOptions.DeliveryConfirmation DCISType 3, DeclaredValue 80) bills TotalCharges 20.79 - the signature and declared-value surcharges are missing from the Shipment Check quote. |  |  | 2026-10-18T10:30:26Z
R3-RETEST-R2-BUG-021 | Options | P3 | retest | Retest R2-BUG-021: insured value never sent to the carrier | ADMIN | MKL246 | API + Carrier API Log | Insurance requested from the carrier and priced | FAIL | STILL OPEN (2/2). UPS Ground purchase with options.insuredValue 500 (order 934334): the UPS ship request in the Carrier API Log carries no InsuredValue/insurance element (only the declared-value element), so no insurance is bought; label cost equals the uninsured rate. |  |  | 2026-10-18T10:30:26Z
R3-ROLE-001 | Security | P1 | positive | Create an operator through Invite user, accept the invite, sign in | ADMIN | MKL246 | UI + API as the operator (USER, MKL246) | Invite, accept and sign-in work; role and client pre-assigned | PASS | Settings > Users > Invite user (qa-1018c-op@example.com, MKL246, role USER - 'day-to-day operator for the client'; the other option is TENANT - customer-facing read-only). 'Invite emailed ... (or logged in dev)' and the raw accept link is shown; pending invite listed with Copy link / Resend / Revoke; admin action logged. Accept page: 'You've been invited to join MKL246 as USER', Full Name / Username / Password (6+ chars). Account qa1018cop created ('Account created - please log in'); sign-in OK ('Welcome back, qa1018cop'), /auth/session = USER, clientCode MKL246. Password set to a generated value kept only in the browser session (cleared afterwards). |  | R3-ROLE-001_invite_issued_with_link.jpg, R3-ROLE-001_accept_invite_page.jpg, R3-ROLE-001_operator_dashboard_qa1018cop.jpg | 2026-10-18T10:54:49Z
R3-ROLE-002 | Security | P1 | positive | Operator can work the orders grid for the own client | ADMIN | MKL246 | UI + API as the operator (USER, MKL246) | Own-client orders listed | FAIL | The Shipment + Label grid is empty for the operator: every GET /api/v1/orders list call (plain, with customer=MKL246, orderNo=, search=, page/size/sort) answers 403 FORBIDDEN 'You do not have permission to perform this action.' while the badges (queue-stats: All 549 / Failed 144 / Archive 405) load; the grid shows 'No orders yet.' and the toast 'Something went wrong - You do not have permission...' on load and on Refresh (2/2, plus 6 API variants). Direct GET /orders/934340 (own order) and /orders/934340/label work, and the operator can validate and buy (934343). | R3-BUG-001 | R3-ROLE-002_operator_orders_grid_403_no_orders.jpg | 2026-10-18T10:54:50Z
R3-ROLE-003 | Security | P1 | abuse | Tenant isolation as the operator (read) | ADMIN | MKL246 | UI + API as the operator (USER, MKL246) | No other tenant's data visible | PASS | GET /orders/900034 (THB000) -> 403; /clients lists only MKL246 (total 1); /carrier-accounts returns the 3 MKL246 accounts (ids 1, 2, 7) and not the platform/QA-1017 ones; /orders/stats and /queue-stats are MKL246-scoped (555 orders); /manifests/events shows MKL246 events; Bulk Mailer import history shows the MKL246 batches; New Shipment client dropdown offers MKL246 only. Residual: GET /clients/{id} answers 403 even for the own client (id 2) while the list works (Low). |  |  | 2026-10-18T10:54:49Z
R3-ROLE-004 | Security | P1 | abuse | Tenant isolation as the operator (write) and admin-only operations | ADMIN | MKL246 | UI + API as the operator (USER, MKL246) | Cross-tenant writes refused with 403; admin operations refused | FAIL | POST /shipments/validate with clientCode THB000 (and with QA-1017-CL01 + account 14, and with an unknown client NOPE99) -> 500 INTERNAL_ERROR 'Something went wrong on the server' (reference ids in server logs) instead of a 403/400 - 3/3; the same bodies as admin answer 200 with clean validation errors ('Account 746W05 belongs to client MKL246, not THB000', '3 issues must be fixed'). Admin-only operations are refused cleanly: POST /api-keys -> 403, POST /carrier-accounts/stamps-sera/add-funds/7 -> 403, GET /api-keys, /admin/carrier-api-log -> 403; /settings/users, /settings/api-keys, /settings/system, /settings/carriers, /settings/clients, /settings/carrier-api-log redirect to /dashboard; the operator's Settings menu is reduced (Clients, Warehouses, Address book, Carrier Accounts, Shipping Catalog, Pickups + End-of-Day, Importer / Broker, Templates, Custom Fields, Notifications, Logs). Operator may void own-client labels (934340 FedEx voided, 934343 UPS void 'rejected' by the sandbox). No THB000 write was attempted (read-only client). | R3-BUG-002 |  | 2026-10-18T10:54:50Z
R3-ROLE-005 | Security | P1 | positive | Sign out, sign back in as admin; test user deactivated | ADMIN | MKL246 | UI + API as the operator (USER, MKL246) | Clean sign-out/sign-in; test account removed | PASS | Clicking the avatar in the left rail logs out at once (toast 'Logged out', no confirmation); /auth/session -> 401 afterwards. Sign-in as admin with the password supplied in chat restored the ADMIN session (/auth/session admin, clientCode null). qa1018cop deactivated from Settings > Users (POST /admin/users/5/deactivate 200, row shows Deactivated); the Deactivate action uses a native browser prompt('Deactivate qa1018cop? Reason (optional):') rather than the app's styled dialogs. The browser's own password manager autofills the admin credentials on the login page (Chrome autofill, not the app - Login.tsx starts with empty state). |  |  | 2026-10-18T10:54:49Z

## New bugs
ID | Severity | Area | Title | Steps to reproduce | Expected | Actual | Impact | Reproduced | Cases | Evidence | Environment | QA status | Dev status | Assigned to | Developer comments | Fixed in build
R3-BUG-001 | High | Security / roles | Operator (USER) role cannot list orders: every GET /api/v1/orders list call answers 403, so the Shipment + Label grid is empty for the role that works it | 1. Invite a USER for MKL246 (Settings > Users > Invite user), accept the invite, sign in. 2. Open Shipment + Label (/orders) or call GET /api/v1/orders?page=0&size=10 (with or without customer=MKL246, search=, orderNo=). | The operator sees the orders of the own client. | 403 FORBIDDEN 'You do not have permission to perform this action.' on every list variant; the grid shows 'No orders yet.' and an error toast while the tab badges (queue-stats) show 549 / 144 / 405. Single-order GET, label, validate, purchase and void work for the same user, so the role is only missing the list permission. | The day-to-day operator role is unusable for its main screen; operators cannot find, reprint, void or re-issue labels without an order number. | 2/2 page loads + Refresh, 6/6 API variants (user qa1018cop, deactivated after the test) | R3-ROLE-002 | R3-ROLE-002_operator_orders_grid_403_no_orders.jpg | UI + API, USER role, MKL246 | Open
R3-BUG-002 | Medium | Security / roles | As an operator, a validate request for another client (or an unknown client) fails with a 500 instead of a clean 403/400 | 1. Sign in as a USER of MKL246. 2. POST /api/v1/shipments/validate with the normal UPS Ground body but clientCode THB000 (also QA-1017-CL01 with account 14, and NOPE99). | 403 (or 400 for the unknown client) with a message; the same body as admin returns 200 with a validation error. | 500 INTERNAL_ERROR 'Something went wrong on the server. Please try again in a moment' with a reference id. No data is returned (isolation holds), but the tenant check throws instead of refusing. | Noisy server errors for a routine permission refusal; error logs fill with what should be a 403; a client-side bug that sends the wrong clientCode is hard to diagnose. | 3/3 (THB000 twice, QA-1017-CL01, NOPE99) | R3-ROLE-004 |  | API, USER role | Open

## Security
ID | Check | Result | Detail | Bugs
R3-RETEST-R2-BUG-019 | Retest R2-BUG-019: Issue API key dialog defaults | FAIL | STILL OPEN (2/2 dialog opens). Settings > API keys > Issue API key still opens with All clients, LIVE and 7/7 scopes preselected (screenshot). One client / TEST / 5 scopes had to be chosen by hand for the QA key.
R3-ROLE-001 | Create an operator through Invite user, accept the invite, sign in | PASS | Settings > Users > Invite user (qa-1018c-op@example.com, MKL246, role USER - 'day-to-day operator for the client'; the other option is TENANT - customer-facing read-only). 'Invite emailed ... (or logged in dev)' and the raw accept link is shown; pending invite listed with Copy link / Resend / Revoke; admin action logged. Accept page: 'You've been invited to join MKL246 as USER', Full Name / Username / Password (6+ chars). Account qa1018cop created ('Account created - please log in'); sign-in OK ('Welcome back, qa1018cop'), /auth/session = USER, clientCode MKL246. Password set to a generated value kept only in the browser session (cleared afterwards).
R3-ROLE-002 | Operator can work the orders grid for the own client | FAIL | The Shipment + Label grid is empty for the operator: every GET /api/v1/orders list call (plain, with customer=MKL246, orderNo=, search=, page/size/sort) answers 403 FORBIDDEN 'You do not have permission to perform this action.' while the badges (queue-stats: All 549 / Failed 144 / Archive 405) load; the grid shows 'No orders yet.' and the toast 'Something went wrong - You do not have permission...' on load and on Refresh (2/2, plus 6 API variants). Direct GET /orders/934340 (own order) and /orders/934340/label work, and the operator can validate and buy (934343). | R3-BUG-001
R3-ROLE-003 | Tenant isolation as the operator (read) | PASS | GET /orders/900034 (THB000) -> 403; /clients lists only MKL246 (total 1); /carrier-accounts returns the 3 MKL246 accounts (ids 1, 2, 7) and not the platform/QA-1017 ones; /orders/stats and /queue-stats are MKL246-scoped (555 orders); /manifests/events shows MKL246 events; Bulk Mailer import history shows the MKL246 batches; New Shipment client dropdown offers MKL246 only. Residual: GET /clients/{id} answers 403 even for the own client (id 2) while the list works (Low).
R3-ROLE-004 | Tenant isolation as the operator (write) and admin-only operations | FAIL | POST /shipments/validate with clientCode THB000 (and with QA-1017-CL01 + account 14, and with an unknown client NOPE99) -> 500 INTERNAL_ERROR 'Something went wrong on the server' (reference ids in server logs) instead of a 403/400 - 3/3; the same bodies as admin answer 200 with clean validation errors ('Account 746W05 belongs to client MKL246, not THB000', '3 issues must be fixed'). Admin-only operations are refused cleanly: POST /api-keys -> 403, POST /carrier-accounts/stamps-sera/add-funds/7 -> 403, GET /api-keys, /admin/carrier-api-log -> 403; /settings/users, /settings/api-keys, /settings/system, /settings/carriers, /settings/clients, /settings/carrier-api-log redirect to /dashboard; the operator's Settings menu is reduced (Clients, Warehouses, Address book, Carrier Accounts, Shipping Catalog, Pickups + End-of-Day, Importer / Broker, Templates, Custom Fields, Notifications, Logs). Operator may void own-client labels (934340 FedEx voided, 934343 UPS void 'rejected' by the sandbox). No THB000 write was attempted (read-only client). | R3-BUG-002
R3-ROLE-005 | Sign out, sign back in as admin; test user deactivated | PASS | Clicking the avatar in the left rail logs out at once (toast 'Logged out', no confirmation); /auth/session -> 401 afterwards. Sign-in as admin with the password supplied in chat restored the ADMIN session (/auth/session admin, clientCode null). qa1018cop deactivated from Settings > Users (POST /admin/users/5/deactivate 200, row shows Deactivated); the Deactivate action uses a native browser prompt('Deactivate qa1018cop? Reason (optional):') rather than the app's styled dialogs. The browser's own password manager autofills the admin credentials on the login page (Chrome autofill, not the app - Login.tsx starts with empty state).
note | localStorage still holds 'multiship_token', an expired JWT (sub admin, role, exp 2026-08-12) from an older auth scheme; the current session is a cookie and the token is not used (session answers 401 after logout), but logout does not clear it. Low - remove on logout / drop the key.
note | Invite acceptance accepts any password of 6+ characters ('123456' enables the button); no complexity or breach check. Low - policy decision.

## Observations
Kind | Observation | Timestamp (UTC)
observation | Return form, 'Return to - your address' block for MKL246: name/company 'MKL' and address 8191 Logistics Dr come from the client record (returnSameAsShipFrom true), but the phone is the client's contact phone +1 555 123 6789 (clients.phone) rather than the return address phone +1 616-772-3513 (shipFrom.phone). Seen in run 3 only (the run-2 return was re-typed by hand); Low - the carrier receives the contact phone instead of the warehouse phone on return labels. | 2026-10-18T10:35:25Z
observation | GET /me/shipper-default returns 'Multiship Warehouse, 1 Warehouse Way, Bengaluru, KA 560001, phone 0000000000' with tenantCode null; this is exactly what the label page preview prints as SHIP FROM (R2-BUG-014) - hypothesis: the preview reads the platform shipper default instead of the order's sender. | 2026-10-18T10:35:25Z
security | localStorage still holds 'multiship_token', an expired JWT (sub admin, role, exp 2026-08-12) from an older auth scheme; the current session is a cookie and the token is not used (session answers 401 after logout), but logout does not clear it. Low - remove on logout / drop the key. | 2026-10-18T10:54:50Z
ux | The avatar button at the bottom of the left rail logs the user out immediately with no confirmation (toast 'Logged out'); an accidental click drops an operator mid-shipment. Low. | 2026-10-18T10:54:50Z
security | Invite acceptance accepts any password of 6+ characters ('123456' enables the button); no complexity or breach check. Low - policy decision. | 2026-10-18T10:54:50Z
ux | Users > Deactivate uses a native browser prompt ('Deactivate <user>? Reason (optional):') while every other destructive action uses the app's styled confirm dialog; the native dialog also blocks automation and screen readers differently. Low. | 2026-10-18T10:54:50Z
observation | The invite dialog says 'Invite emailed ... (or logged in dev)' and shows the raw accept link as a fallback; whether an email actually left the box was not verified (Email Delivery Log not checked). | 2026-10-18T10:54:50Z
observation | Operator (USER) sees Clients, Warehouses, Carrier Accounts, Shipping Catalog and Custom Fields in Settings; their write actions were not exercised as USER (the role's read scope looked client-limited: /clients total 1, /carrier-accounts 3). | 2026-10-18T10:54:50Z

## Test data (cleanup)
What | Id | Where | State | Note | Created (UTC)
order | 934329, 934330 | MKL246 | GENERATED (UPS 2-box, FedEx 2-box) | QA-1018c multi-box declared-value retest (R2-BUG-004) | 2026-10-18T10:24:45Z
order | 934331, 934332 | MKL246 | GENERATED (same reference QA-1018c-D001 twice) | duplicate purchase retest (R2-BUG-005) | 2026-10-18T10:24:45Z
order | 934333 | MKL246 | GENERATED (FedEx Ground, ADULT signature) | surcharge quote retest (R2-BUG-020) | 2026-10-18T10:24:45Z
order | 934334 | MKL246 | GENERATED (insuredValue 500) | insured value retest (R2-BUG-021) | 2026-10-18T10:24:45Z
order | 934335, 934336, 934337 | MKL246 | VOIDED on the platform only (no carrier cancel) - External API, refs QA-1018c-EXT1 (x2) and QA-1018c-EXT2 | R2-BUG-001 / R2-BUG-005 retest; labels never used | 2026-10-18T10:24:45Z
External API key | QA-1018c-key (id 3, MKL246, TEST, scopes shipments tracking rates void addresses) ...087d | Settings > API keys | REVOKED at 15:53 local (revoked token -> 401) | token kept in the browser session only and cleared; never written anywhere | 2026-10-18T10:24:45Z
pickup attempts | FedEx / UPS / USPS pickup requests (all rejected by the carriers) | Pickups, MKL246 | no pickup scheduled | R2-BUG-002 retest | 2026-10-18T10:24:45Z
bulk import | Import #13 (QA-1018c-bulk2.csv), label batch 34; uploads 24 and 25 discarded | Bulk Mailer > Import history | Complete - 2 generated | R2-BUG-007 retest | 2026-10-18T10:27:33Z
order | 934338, 934339 | MKL246 | GENERATED (UPS P80 / FedEx F77 from import #13), refs QA-1018c-BM-2 / QA-1018c-BM-1 | bulk label run | 2026-10-18T10:27:33Z
order | 934339 | MKL246 | label 794893822638 VOIDED at the carrier (FedEx cancel 2722), reissued as 794893823895 (GENERATED) | R2-BUG-016 retest | 2026-10-18T10:33:29Z
order | 934340 | MKL246 | GENERATED (FedEx Ground 794893824160), ref QA-1018c-CF1, customFields {} | R2-BUG-008 retest (UI) | 2026-10-18T10:37:44Z
custom field definition | qa_1018c_dept (MKL246) | Settings > Custom Fields | created and deleted during the retest | R2-BUG-008 | 2026-10-18T10:37:44Z
order | 934341, 934342 | MKL246 | ERROR (carrierCode/account mismatch probe, no label) | run-1 BUG-005 retest | 2026-10-18T10:40:25Z
user | qa1018cop (qa-1018c-op@example.com, USER, MKL246, id 5) | Settings > Users | Deactivated after the role tests (reason 'QA-1018c cleanup'); password kept only in the browser session and cleared | invite accepted during run 3; reactivate or delete as you prefer | 2026-10-18T10:54:50Z
order | 934343 | MKL246 | GENERATED (UPS Ground, bought by the operator qa1018cop), ref QA-1018c-OP1; void attempt rejected by the UPS sandbox | role test | 2026-10-18T10:54:50Z
order | 934340 (update) | MKL246 | label 794893824160 VOIDED by the operator during the role test | R2-BUG-008 order | 2026-10-18T10:54:50Z