## Summary
multiship QA regression — 2026-10-18
Verdict: not ready to release as is — fix BUG-007 and BUG-017 (High), re-test multi-box declared values and close-out; cover role gating, NDS/D2C and the held submits before go-live.
Cases | Pass | Fail | Blocked | Not run | Total
| 82 | 24 | 12 | 0 | 118
Bugs | Critical | High | Medium | Low | Total
| 0 | 2 | 9 | 9 | 20
Area | Pass | Fail | Blocked | Total
Environment | 1 | 0 | 1 | 2
New shipment | 2 | 2 | 0 | 4
Manual shipment | 4 | 0 | 0 | 4
Validation | 18 | 4 | 1 | 23
Rates/services | 4 | 0 | 2 | 6
Carrier services | 12 | 0 | 0 | 12
International | 8 | 0 | 0 | 8
Options | 1 | 2 | 0 | 3
Label output | 0 | 1 | 0 | 1
Void / reissue | 3 | 1 | 1 | 5
Returns | 0 | 1 | 0 | 1
Orders grid | 2 | 4 | 0 | 6
Bulk Mailer | 8 | 4 | 0 | 12
API Batches / D2C | 2 | 0 | 2 | 4
Close out / pickups | 1 | 1 | 2 | 4
Add Funds | 2 | 2 | 1 | 5
Settings | 1 | 0 | 0 | 1
Data integrity | 2 | 2 | 1 | 5
Security | 11 | 0 | 1 | 12
Environment | Local dev; test stack confirmed by user 2026-10-18; carriers on sandbox hosts (verified in Carrier API Log)
Base URL | http://localhost:5173
Tester | Claude (Cowork) driving Claude in Chrome
Session | ADMIN user 'admin' via the already-open browser session
Write client | MKL246 only
Read-only clients | QA-1017-CL01, THB000
Carriers | FedEx, UPS, USPS (Stamps/SERA) sandbox
Depth | Full regression
Yellow columns | Dev status / Assigned to / Developer comments / Fixed in build are for the development team to fill in.

## Test cases
ID | Area | Priority | Kind | Title | Role | Client | Method | Expected | Result | Actual / notes | Bugs | Evidence | Timestamp (UTC) | Dev status | Assigned to | Developer comments | Fixed in build
ENV-001 | Environment | P1 | positive | Carrier hosts are sandbox only | ADMIN | - |  | Only sandbox hosts and SANDBOX accounts | PASS | FedEx apis-sandbox.fedex.com, UPS wwwcie.ups.com, Stamps api.testing.stampsendicia.com; all 5 accounts SANDBOX |  | ENV-carrier_accounts_all_sandbox.jpg
ENV-002 | Environment | P1 | positive | NDS (Oracle) connectivity | ADMIN | - |  | oracleDataSource UP | BLOCKED | oracleDataSource OUT_OF_SERVICE, /actuator/health 503; ndsWriter reports UP at the same time; nds-default connection Inactive and tagged PROD |  | ENV-dashboard_system_status_oracle_out_of_service.jpg
SHP-MB-001 | New shipment | P1 | positive | Multi-box UPS Ground (3 boxes, different weights/dims/declared values) through the UI | ADMIN | MKL246 | UI + API replay of POST /api/v1/orders/manual-label | Clear, correct refusal or success | FAIL | Order 934238: packageCount 3, total 12.5 lb, master + 3 child tracking numbers, correct per-box weights and dimensions on the carrier request, PKG 1/3 label. But the declared values typed per box (80/60/40) were replaced on the carrier request by the box-1 value split evenly (26.67/26.67/26.66). | BUG-007 |  | 2026-10-18T03:49:46Z
SHP-MB-002 | New shipment | P1 | positive | Two-box UPS Ground and FedEx Ground by API with per-box declared values 50 and 150 | ADMIN | MKL246 | UI + API replay of POST /api/v1/orders/manual-label | Clear, correct refusal or success | FAIL | UPS order 934239 and FedEx order 934240 both GENERATED; carrier requests carry 25 and 25 on each box (50 split evenly) instead of 50 and 150. | BUG-007 |  | 2026-10-18T03:49:46Z
SHP-UPS-002 | New shipment | P1 | positive | UPS Worldwide Saver US->CA, 1 box, customs items, FTR NOEEI 30.36, DAP | ADMIN | MKL246 |  | International UPS services offered; validation requires FTR/AES; label + commercial invoice generated; order stored with intl=Y | PASS | Order 934205 GENERATED. Services offered for CA: UPS Worldwide Saver/Expedited/Express. Shipment Check all 5 sections passed; rate USD 58.10 (transit time not given, billed wt 4 lb). Order JSON: intl=Y, ref QA-1018-T005, shipVia 65, shipViaDescription null, tracking 1ZXXXXXXXXXXXXXXXX (UPS CIE placeholder), ZPL is graphic (no text fields to read). Commercial invoice prints correct exporter (MKL, Zeeland MI), consignee, HS 6109.10.00, qty 1, total 20.00, DAP, NO EEI 30.36. Label preview still shows wrong ship-from (BUG-001, 3rd repro). | BUG-002 | SHP-UPS-002_label_preview_934205.jpg, SHP-UPS-002_commercial_invoice_934205.jpg, SHP-UPS-002_shipment_check_passed.jpg | 2026-10-18T03:32:56Z
SHP-USP-002 | New shipment | P1 | positive | USPS Priority Mail International US->GB, 1 box, DAP, NOEEI 30.37(a) | ADMIN | MKL246 |  | USPS intl services offered; label + commercial invoice; order intl=Y | PASS | Order 934206 GENERATED via PRIORITY_INTL, intl=Y, ref QA-1018-T006. USPS intl services offered: Priority Mail Intl, Priority Mail Express Intl. Shipment Check: all passed, 1 warning (USPS normalised the address; review before shipping). Rate USD 74.42, billed 3.45 lb on box size vs 2 lb actual (message explains). Tracking CJ000000005US is the same sandbox number as 3 earlier USPS orders. Invoice correct (DAP, consignee pays, HS 6109.10.00, 25.00). Label preview wrong ship-from again (BUG-001). | BUG-002 | SHP-USP-002_label_preview_934206.jpg, SHP-USP-002_commercial_invoice_934206.jpg, SHP-USP-002_shipment_check_price_dimweight.jpg | 2026-10-18T03:32:56Z
SHP-FDX-001 | Manual shipment | P1 | positive | FedEx Ground, US to US, 1 box, ZPL 4x6, MKL246 / 3PL-EAST | ADMIN | MKL246 |  | Validation passes, label generated, order GENERATED with tracking, ZPL carries sender/recipient/ref/weight, grid and API agree | PASS | Order 934201 GENERATED, tracking 794893800699, grid row and API agree, ZPL correct (sender MKL Zeeland, ref, weight 2.5). First Validate showed 'FEDEX rate call failed - server error'; Check again passed. Billed weight 3.11 lb (dim weight) shown correctly. |  | SHP-FDX-001_shipment_check_rate_call_failed.jpg, SHP-FDX-001_label_preview_934201.jpg
SHP-FDX-002 | Manual shipment | P1 | positive | FedEx International Priority US to GB, 1 box, DAP, 1 commercial-invoice line | ADMIN | MKL246 |  | Customs check passes, commercial invoice generated, label generated | PASS | Order 934204 GENERATED, INTERNATIONAL_PRIORITY, tracking 794893801250. Origin is required per item (refused with 'Country of origin is required' until set). FedEx sandbox rate quote returned 503 after 12-13 s on both attempts; label purchase still allowed, price not shown.
SHP-UPS-001 | Manual shipment | P1 | positive | UPS Ground (03), US to US, 1 box, MKL246 / 3PL-EAST | ADMIN | MKL246 |  | Validation passes, label generated, order GENERATED with tracking, ZPL correct | PASS | Order 934202 GENERATED, shipVia 03, validation all passed. Sandbox (UPS CIE) returns placeholder tracking 1ZXXXXXXXXXXXXXXXX, so tracking is not unique across UPS sandbox labels. |  | SHP-UPS-001_label_preview_934202.jpg
SHP-USP-001 | Manual shipment | P1 | positive | USPS Ground Advantage, US to US, 1 box, ZPL, MKL246 / 3PL-EAST | ADMIN | MKL246 |  | Validation passes; label generated; tracking stored | PASS | Order 934203 GENERATED, GROUND_ADVANTAGE, tracking 9400111969000940000011, ZPL 10,347 chars with Zeeland sender. Note: Validate with empty Label type does nothing except an inline 'Required - pick a label type' (USPS has no default label type, FedEx defaults to ZPL).
VAL-API-001 | Validation | P1 | negative | Weight 0 refused | ADMIN | MKL246 | API replay of POST /api/v1/shipments/validate (UI request body) | Clear, correct refusal or success | PASS | UPS Ground: 'A shipment weight greater than zero is required.' Carrier call skipped. |  |  | 2026-10-18T03:38:54Z
VAL-API-002 | Validation | P3 | negative | Weight -1 refused | ADMIN | MKL246 | API replay of POST /api/v1/shipments/validate (UI request body) | Clear, correct refusal or success | PASS | Refused, but the negative weight is still forwarded to UPS (message 'UPS Time-in-Transit rejected the request: invalid Weight'), unlike weight 0 where the carrier check is skipped. Harmless in validate; inconsistent guard. |  |  | 2026-10-18T03:38:54Z
VAL-API-003 | Validation | P2 | boundary | Weight 0.01 lb accepted and quoted | ADMIN | MKL246 | API replay of POST /api/v1/shipments/validate (UI request body) | Clear, correct refusal or success | PASS | Quoted USD 10.90. No minimum weight enforced locally (carriers bill a 1 lb minimum). Observation only. |  |  | 2026-10-18T03:38:54Z
VAL-API-004 | Validation | P1 | boundary | Weight at limit 150 lb (UPS Ground) accepted | ADMIN | MKL246 | API replay of POST /api/v1/shipments/validate (UI request body) | Clear, correct refusal or success | PASS | PASS, USD 83.71. |  |  | 2026-10-18T03:38:54Z
VAL-API-005 | Validation | P1 | boundary | Weight 150.01 lb refused | ADMIN | MKL246 | API replay of POST /api/v1/shipments/validate (UI request body) | Clear, correct refusal or success | PASS | 'Box 1: 150.01 lb exceeds UPS 03 parcel weight limit of 150 lb. Requires LTL freight service'. |  |  | 2026-10-18T03:38:54Z
VAL-API-006 | Validation | P2 | negative | Non-numeric weight 'abc' | ADMIN | MKL246 | API replay of POST /api/v1/shipments/validate (UI request body) | Clear, correct refusal or success | PASS | HTTP 400 MALFORMED_REQUEST with a readable message; no stack trace. |  |  | 2026-10-18T03:38:54Z
VAL-API-007 | Validation | P2 | negative | Null weight and absurd weight 99,999,999 | ADMIN | MKL246 | API replay of POST /api/v1/shipments/validate (UI request body) | Clear, correct refusal or success | PASS | Both refused with clear messages. |  |  | 2026-10-18T03:38:54Z
VAL-API-008 | Validation | P1 | boundary | Dimension boundaries: length 0, width -5, length 108, 109, L+G 300 | ADMIN | MKL246 | API replay of POST /api/v1/shipments/validate (UI request body) | Clear, correct refusal or success | PASS | 0 and -5 refused ('Pick a package preset OR fill in custom dimensions. Missing: ...'); 108 PASS; 109 refused; L+G 300 refused (limit 165). |  |  | 2026-10-18T03:38:54Z
VAL-API-009 | Validation | P2 | boundary | Unit conversion: cm dimensions, kg weights (70 kg refused, 68 kg accepted) | ADMIN | MKL246 | API replay of POST /api/v1/shipments/validate (UI request body) | Clear, correct refusal or success | PASS | 70 kg = 154.32 lb refused; 68 kg accepted; cm accepted. |  |  | 2026-10-18T03:38:54Z
VAL-API-010 | Validation | P1 | negative | Required recipient fields (name, address line 1, city, state, ZIP, country) each missing | ADMIN | MKL246 | API replay of POST /api/v1/shipments/validate (UI request body) | Clear, correct refusal or success | PASS | Each refused with its own message; UPS sandbox accepts missing fields and the app flags that ('UPS accepted a payload with missing required fields - sandbox...'). |  |  | 2026-10-18T03:38:54Z
VAL-API-011 | Validation | P1 | negative | ZIP formats: '1234', 'ABCDE' refused; '10118-1234' accepted; state/ZIP mismatch; state ZZ | ADMIN | MKL246 | API replay of POST /api/v1/shipments/validate (UI request body) | Clear, correct refusal or success | PASS | 'ZIP 10118 is in NY, not CA - correct the state or the ZIP.' and 'Postal code ... doesn't match the US format' as expected. |  |  | 2026-10-18T03:38:54Z
VAL-API-012 | Validation | P2 | negative | Empty recipient phone | ADMIN | MKL246 | API replay of POST /api/v1/shipments/validate (UI request body) | Clear, correct refusal or success | FAIL | Only a warning ('Recipient phone is recommended'); the UI marks phone required with 10 digits. Server rule is weaker than the UI rule. | BUG-003 |  | 2026-10-18T03:38:54Z
VAL-API-013 | Validation | P1 | negative | Garbage recipient phone ('abc', '12345') and email ('not-an-email') | ADMIN | MKL246 | API replay of POST /api/v1/shipments/validate (UI request body) | Clear, correct refusal or success | FAIL | All PASS with a quote. No server-side phone or email format check. | BUG-003 |  | 2026-10-18T03:38:54Z
VAL-API-014 | Validation | P1 | boundary | Over-long fields: name 36/120, address 36/300, reference 36/5000 chars | ADMIN | MKL246 | API replay of POST /api/v1/shipments/validate (UI request body) | Clear, correct refusal or success | FAIL | All PASS. UPS limits name, address lines and reference to 35 characters, so production would reject at label time. | BUG-004 |  | 2026-10-18T03:38:54Z
VAL-API-015 | Validation | P2 | boundary | City 70 chars | ADMIN | MKL246 | API replay of POST /api/v1/shipments/validate (UI request body) | Clear, correct refusal or success | PASS | Refused by the carrier ('invalid DestinationPostalAndCity'). |  |  | 2026-10-18T03:38:54Z
VAL-API-017 | Validation | P2 | negative | PO Box: UPS refused, USPS accepted | ADMIN | MKL246 | API replay of POST /api/v1/shipments/validate (UI request body) | Clear, correct refusal or success | PASS | UPS: 'UPS can't deliver to a PO box ...'; USPS Ground Advantage PASS. |  |  | 2026-10-18T03:38:54Z
VAL-API-018 | Validation | P2 | positive | Special destinations: APO (USPS), HI, AK, PR, GU (UPS Ground) | ADMIN | MKL246 | API replay of POST /api/v1/shipments/validate (UI request body) | Clear, correct refusal or success | PASS | APO PASS 11.51; HI/AK PASS 38.96; PR and GU refused for UPS Ground ('does not deliver to PR'), treated as international. |  |  | 2026-10-18T03:38:54Z
VAL-API-019 | Validation | P2 | positive | USPS Ground Advantage to Puerto Rico | ADMIN | MKL246 | API replay of POST /api/v1/shipments/validate (UI request body) | Clear, correct refusal or success | BLOCKED | App treats PR as international (international=true, needs incoterms, commodity lines, invoice total). USPS treats PR as domestic. Needs product confirmation and a UI check (does the form show Customs/Items for PR?). |  |  | 2026-10-18T03:38:54Z
VAL-API-020 | Validation | P1 | negative | Account/service mismatch: UPS account with FedEx service, unknown service id, unknown account | ADMIN | MKL246 | API replay of POST /api/v1/shipments/validate (UI request body) | Clear, correct refusal or success | PASS | Each refused with a clear message (service list offered for the lane). |  |  | 2026-10-18T03:38:54Z
VAL-API-021 | Validation | P2 | negative | carrierCode inconsistent with account (FOO / FEDEX with a UPS account) | ADMIN | MKL246 | API replay of POST /api/v1/shipments/validate (UI request body) | Clear, correct refusal or success | FAIL | Validate passes carrierCode FOO. On purchase, carrierCode FEDEX with a UPS account makes the server call FedEx with the UPS account (HTTP 502 'FedEx rejected the credentials', order saved as ERROR 934211/934212). Server trusts the body's carrierCode instead of the account. | BUG-005 |  | 2026-10-18T03:38:54Z
VAL-API-022 | Validation | P2 | boundary | USPS weight 70 accepted, 70.01 refused | ADMIN | MKL246 | API replay of POST /api/v1/shipments/validate (UI request body) | Clear, correct refusal or success | PASS | 70 lb PASS 118.67; 70.01 refused (limit 70). |  |  | 2026-10-18T03:38:54Z
VAL-GB-001 | Validation | P2 | negative | Country-specific recipient phone length (GB 9-10 digits) and incoterm rule for USPS intl | ADMIN | MKL246 |  | Inline errors that say what to fix | PASS | Validate refused: toast '2 fields need attention - Incoterms: choose DAP or DDP - and 1 other field highlighted in red'; phone field red with 'GB phone numbers are 9-10 digits (you entered 13)'. Both fixed, validate passed. Note: the Incoterms list offered DDU for a USPS shipment yet validation says only DAP or DDP are allowed. |  | VAL-GB-001_incoterms_and_phone_errors.jpg | 2026-10-18T03:32:35Z
VAL-INTL-001 | Validation | P1 | negative | International UPS shipment without FTR exemption or AES ITN is blocked at Validate | ADMIN | MKL246 |  | Validation refuses with a clear message; Generate stays locked | PASS | Validate refused with toast: 1 field needs attention - Pick FTR exemption (pick NOEEI 30.36 for Canada) or AES ITN before validating - the selected account has no saved default. Generate stayed locked. Note: the toast disappears within about 6 s and the Customs step pill gets no error styling, so a slow reader can miss why nothing happened. |  | SHP-UPS-002_validate_blocked_toast_FTR.jpg | 2026-10-18T03:29:27Z
PRC-FDX-001 | Rates/services | P2 | positive | FedEx quote vs actual label cost (Ground, Express Saver, 2Day, Std Overnight, Priority Overnight) | ADMIN | MKL246 | API replay of POST /api/v1/orders/manual-label + order GET + carrier log check | Clear, correct refusal or success | BLOCKED | Ground and Express Saver match exactly. 2Day quote 58.29 vs cost 41.49 (-29%), Standard Overnight 126.56 vs 109.76, Priority Overnight 143.08 vs 126.28. FedEx rate and ship responses share the same base charge (35.06 for 2Day) but differ in surcharges; the sandbox is a likely cause. Verify on production-like credentials. |  |  | 2026-10-18T03:52:30Z
PRC-USP-001 | Rates/services | P2 | positive | USPS label cost recorded | ADMIN | MKL246 | UI + API replay of POST /api/v1/orders/manual-label | Clear, correct refusal or success | BLOCKED | USPS GA labels (orders 934234, 934237) store shippingCost 0 while the quote was 7.78; the Stamps sandbox response itself says amount 0.00. Cannot judge cost capture in sandbox; verify on production-like rates. |  |  | 2026-10-18T03:49:46Z
SVC-FDX-001 | Rates/services | P1 | positive | FedEx domestic rate quotes: Ground, Express Saver, 2Day, Standard Overnight, Priority Overnight | ADMIN | MKL246 | API replay of POST /api/v1/shipments/validate (UI request body) | Clear, correct refusal or success | PASS | Ground 22.26, Express Saver 36.72, 2Day 58.29, Standard Overnight 126.56, Priority Overnight 143.08 (4 lb 10x8x6, MI to NY 10118). |  |  | 2026-10-18T03:38:54Z
SVC-FDX-002 | Rates/services | P2 | negative | FedEx Home Delivery to a non-residential address refused | ADMIN | MKL246 | API replay of POST /api/v1/shipments/validate (UI request body) | Clear, correct refusal or success | PASS | 'FedEx Home Delivery only delivers to homes - tick Residential address on Ship to, or pick another service.' |  |  | 2026-10-18T03:38:54Z
SVC-UPS-001 | Rates/services | P1 | positive | UPS domestic rate quotes: Ground, 3 Day Select, 2nd Day Air, Next Day Air | ADMIN | MKL246 | API replay of POST /api/v1/shipments/validate (UI request body) | Clear, correct refusal or success | PASS | Ground 11.33, 3 Day 18.98, 2nd Day 21.67, Next Day 42.18. |  |  | 2026-10-18T03:38:54Z
SVC-USP-001 | Rates/services | P1 | positive | USPS domestic rate quotes: Ground Advantage, Priority, Priority Express | ADMIN | MKL246 | API replay of POST /api/v1/shipments/validate (UI request body) | Clear, correct refusal or success | PASS | GA 7.78, Priority 14.67, Express 71.49. |  |  | 2026-10-18T03:38:54Z
SHP-FDX-003 | Carrier services | P1 | positive | FedEx Home Delivery label purchase (residential flag set) | ADMIN | MKL246 | API replay of POST /api/v1/orders/manual-label + order GET + carrier log check | Clear, correct refusal or success | PASS | Order 934241 via GROUND_HOME_DELIVERY, cost 31.76, unique FedEx tracking. |  |  | 2026-10-18T03:52:30Z
SHP-FDX-004 | Carrier services | P1 | positive | FedEx Express Saver label purchase | ADMIN | MKL246 | API replay of POST /api/v1/orders/manual-label + order GET + carrier log check | Clear, correct refusal or success | PASS | Order 934242, cost 36.72 = quote 36.72. |  |  | 2026-10-18T03:52:30Z
SHP-FDX-005 | Carrier services | P1 | positive | FedEx 2Day label purchase | ADMIN | MKL246 | API replay of POST /api/v1/orders/manual-label + order GET + carrier log check | Clear, correct refusal or success | PASS | Order 934243, cost 41.49; quote was 58.29 (see PRC-FDX-001). |  |  | 2026-10-18T03:52:30Z
SHP-FDX-006 | Carrier services | P1 | positive | FedEx Standard Overnight label purchase | ADMIN | MKL246 | API replay of POST /api/v1/orders/manual-label + order GET + carrier log check | Clear, correct refusal or success | PASS | Order 934244, cost 109.76; quote was 126.56. |  |  | 2026-10-18T03:52:30Z
SHP-FDX-007 | Carrier services | P1 | positive | FedEx Priority Overnight label purchase | ADMIN | MKL246 | API replay of POST /api/v1/orders/manual-label + order GET + carrier log check | Clear, correct refusal or success | PASS | Order 934245, cost 126.28; quote was 143.08. |  |  | 2026-10-18T03:52:30Z
SHP-UPS-003 | Carrier services | P1 | positive | UPS Ground label purchase (domestic) | ADMIN | MKL246 | API replay of POST /api/v1/orders/manual-label + order GET + carrier log check | Clear, correct refusal or success | PASS | Order 934224 GENERATED, via 03, ZPL present, tracking placeholder (CIE). Cost 11.44 vs quote 11.33. |  |  | 2026-10-18T03:52:30Z
SHP-UPS-004 | Carrier services | P1 | positive | UPS 3 Day Select label purchase | ADMIN | MKL246 | API replay of POST /api/v1/orders/manual-label + order GET + carrier log check | Clear, correct refusal or success | PASS | Order 934222 via 12, cost 19.17 vs quote 18.98. |  |  | 2026-10-18T03:52:30Z
SHP-UPS-005 | Carrier services | P1 | positive | UPS 2nd Day Air label purchase | ADMIN | MKL246 | API replay of POST /api/v1/orders/manual-label + order GET + carrier log check | Clear, correct refusal or success | PASS | Order 934223 via 02, cost 21.89 vs quote 21.67. |  |  | 2026-10-18T03:52:30Z
SHP-UPS-006 | Carrier services | P1 | positive | UPS Next Day Air label purchase | ADMIN | MKL246 | API replay of POST /api/v1/orders/manual-label + order GET + carrier log check | Clear, correct refusal or success | PASS | Order 934221 via 01, cost 42.61 vs quote 42.18. |  |  | 2026-10-18T03:52:30Z
SHP-USP-003 | Carrier services | P1 | positive | USPS Ground Advantage label purchase | ADMIN | MKL246 | API replay of POST /api/v1/orders/manual-label + order GET + carrier log check | Clear, correct refusal or success | PASS | Orders 934234/934237/934248 GENERATED via GROUND_ADVANTAGE; cost 0 (sandbox returns amount 0.00). |  |  | 2026-10-18T03:52:30Z
SHP-USP-004 | Carrier services | P1 | positive | USPS Priority Mail label purchase | ADMIN | MKL246 | API replay of POST /api/v1/orders/manual-label + order GET + carrier log check | Clear, correct refusal or success | PASS | Order 934246 via PRIORITY. |  |  | 2026-10-18T03:52:30Z
SHP-USP-005 | Carrier services | P1 | positive | USPS Priority Mail Express label purchase | ADMIN | MKL246 | API replay of POST /api/v1/orders/manual-label + order GET + carrier log check | Clear, correct refusal or success | PASS | Order 934247 via PRIORITY_EXPRESS. |  |  | 2026-10-18T03:52:30Z
CMP-EMB-001 | International | P1 | negative | Embargoed destinations (Cuba, Iran, North Korea, Syria) through UPS, FedEx and USPS | ADMIN | MKL246 | API replay of POST /api/v1/orders/manual-label (international body: items, incoterms, reason, FTR) | Clear, correct refusal or success | PASS | All carriers refuse (UPS 120124/120208, FedEx DESTINATION..., Stamps 400); orders 934270-934273 saved as ERROR. The app has no destination or denied-party check of its own: it relies on carrier errors, and UPS validate fails with generic messages such as 'invalid DestinationCountryCode'. |  |  | 2026-10-18T03:55:36Z
INT-FDX-001 | International | P1 | positive | FedEx International Economy to CA, GB, DE | ADMIN | MKL246 | API replay of POST /api/v1/orders/manual-label (international body: items, incoterms, reason, FTR) | Clear, correct refusal or success | PASS | Orders 934266, 934265, 934264 GENERATED, unique FedEx tracking. Costs 153.09, 229.75, 232.40; quote for CA 153.09 equals cost. |  |  | 2026-10-18T03:55:36Z
INT-FDX-002 | International | P1 | positive | FedEx International Priority to CA, GB, DE | ADMIN | MKL246 | API replay of POST /api/v1/orders/manual-label (international body: items, incoterms, reason, FTR) | Clear, correct refusal or success | PASS | Orders 934268, 934267, 934269 GENERATED. Costs 181.18, 240.02, 242.67; quote for GB 240.02 equals cost. |  |  | 2026-10-18T03:55:36Z
INT-UPS-001 | International | P1 | positive | UPS Worldwide Saver to CA, GB, MX | ADMIN | MKL246 | API replay of POST /api/v1/orders/manual-label (international body: items, incoterms, reason, FTR) | Clear, correct refusal or success | PASS | Orders 934249 (CA), 934250 (GB), 934251 (MX) GENERATED, via 65, intl=Y. Cost within 1% above quote (58.10/58.69, 88.74/89.64, 69.73/70.43). |  |  | 2026-10-18T03:55:36Z
INT-UPS-002 | International | P1 | positive | UPS Worldwide Expedited to CA, GB, MX | ADMIN | MKL246 | API replay of POST /api/v1/orders/manual-label (international body: items, incoterms, reason, FTR) | Clear, correct refusal or success | PASS | Orders 934253, 934252, 934254 GENERATED via 08. Costs 40.62, 55.03, 46.12 vs quotes 40.21, 54.48, 45.66. |  |  | 2026-10-18T03:55:36Z
INT-UPS-003 | International | P1 | positive | UPS Worldwide Express to CA, GB, MX | ADMIN | MKL246 | API replay of POST /api/v1/orders/manual-label (international body: items, incoterms, reason, FTR) | Clear, correct refusal or success | PASS | Orders 934255, 934256, 934257 GENERATED via 07. Costs 62.71, 90.98, 71.60 vs quotes 62.08, 90.07, 70.88. |  |  | 2026-10-18T03:55:36Z
INT-USP-001 | International | P1 | positive | USPS Priority Mail International to CA, GB, AU | ADMIN | MKL246 | API replay of POST /api/v1/orders/manual-label (international body: items, incoterms, reason, FTR) | Clear, correct refusal or success | PASS | CA 934259 and GB 934260 GENERATED (validate WARN: address normalised). AU: validate PASS with a quote of 93.65 but the carrier refused the label (order 934262 ERROR): 'USPS has temporarily suspended Priority Mail International shipments to the selected country'. Carrier-side suspension; error passed through to the user as raw JSON text. |  |  | 2026-10-18T03:55:36Z
INT-USP-002 | International | P1 | positive | USPS Priority Mail Express International to CA, GB, AU | ADMIN | MKL246 | API replay of POST /api/v1/orders/manual-label (international body: items, incoterms, reason, FTR) | Clear, correct refusal or success | PASS | Orders 934261, 934258, 934263 GENERATED via EXPRESS_INTL; cost 0 (sandbox). |  |  | 2026-10-18T03:55:36Z
OPT-ACC-001 | Options | P1 | positive | Accessorial pricing: residential, signature (indirect/direct/adult) vs quote, UPS Ground 4 lb | ADMIN | MKL246 | UI + API replay of POST /api/v1/orders/manual-label | Clear, correct refusal or success | FAIL | Shipment Check quote 11.33 in every case. Actual label cost: base 11.44, residential 11.44 (no surcharge), indirect 19.14, direct 19.14, adult 20.79; declared value over 100 adds charges (150: +4.90, 200: +5.10, 500: +8.50). Quote ignores signature and declared-value charges. | BUG-008 |  | 2026-10-18T03:49:46Z
OPT-INS-001 | Options | P2 | negative | UI blocks Insured value above Declared value | ADMIN | MKL246 | UI + API replay of POST /api/v1/orders/manual-label | Clear, correct refusal or success | PASS | Toast 'Insured value: Insured value cannot exceed declared value' and red field error. |  |  | 2026-10-18T03:49:46Z
OPT-INS-002 | Options | P1 | negative | Insured value above declared value by API; does the insured amount reach the carrier | ADMIN | MKL246 | UI + API replay of POST /api/v1/orders/manual-label | Clear, correct refusal or success | FAIL | API accepts insured 200/300 with declared 80 (WARN only). The UPS and FedEx requests carry only the declared value (80), and the USPS request has no value field at all, so the insured amount is never sent to any carrier. The form itself prevents insured > declared, so this only matters for API callers. | BUG-009 |  | 2026-10-18T03:49:46Z
LBL-001 | Label output | P2 | positive | Label screen preview matches the shipment (ship-from, reference) | ADMIN | MKL246 |  | Preview shows the same ship-from and reference as the shipment and the ZPL | FAIL | Preview for orders 934201 (FedEx) and 934202 (UPS) shows SHIP FROM 'Multiship Warehouse, 1 Warehouse Way, Bengaluru KA 560001' and REF = order number, while the shipment sender is MKL, 8191 Logistics Dr, Zeeland MI 49464 and PO is QA-1018-T00x. preview.png HEAD returns 503 and the UI falls back to a text label. The stored ZPL and the FedEx request carry the correct Zeeland sender. | BUG-001 | SHP-FDX-001_label_preview_934201.jpg, SHP-UPS-001_label_preview_934202.jpg | 2026-10-18T03:16:42Z
VOID-001 | Void / reissue | P1 | positive | Void a FedEx label (single box and 2-box) via POST /orders/{id}/void | ADMIN | MKL246 | UI + API replay | Clear, correct refusal or success | PASS | Orders 934242 and 934240: '1 batch(es) voided', carrier cancel PUT 200, label status VOIDED, grid shows VOID and offers 'Reissue label'. Note orderDetails.status still reads GENERATED in the order JSON. |  |  | 2026-10-18T03:58:53Z
VOID-002 | Void / reissue | P1 | positive | Void a UPS label (UI confirm dialog) | ADMIN | MKL246 | UI + API replay | Clear, correct refusal or success | BLOCKED | UI dialog is clear (cannot be undone, refund only before first scan). UPS CIE rejects the cancel because the sandbox tracking number is the placeholder 1ZXXXXXXXXXXXXXXXX ('No shipment found within the allowed void period'); order stays GENERATED and the toast shows the carrier reason. |  |  | 2026-10-18T03:58:53Z
VOID-003 | Void / reissue | P1 | positive | Void a USPS label | ADMIN | MKL246 | UI + API replay | Clear, correct refusal or success | FAIL | POST /orders/934246/void and /934247/void return 502 'USPS void call failed for 9400111969000940000011: Query did not return a unique result: 158 results were returned'. The sandbox reuses one tracking number on every label, and the void looks the label up by tracking number. The raw persistence-layer message is shown to the user. | BUG-010 |  | 2026-10-18T03:58:53Z
VOID-004 | Void / reissue | P2 | negative | Void edge cases: already voided, ERROR order, unknown order, non-numeric id | ADMIN | MKL246 | UI + API replay | Clear, correct refusal or success | PASS | Already voided: 200 'Order 934242 was already voided.' ERROR order: 404 VALIDATION_ERROR 'has no tracking number to void'. Unknown order 999999999: same 404 text (does not say the order does not exist). Non-numeric id: 400 MALFORMED_REQUEST. |  |  | 2026-10-18T03:58:53Z
VOID-005 | Void / reissue | P1 | positive | Reissue a voided FedEx label from the grid | ADMIN | MKL246 | UI: New return form + carrier log | Clear, correct refusal or success | PASS | 'Reissue label' opens the form with a banner (previous label voided, order keeps its number); duplicate-reference warning shown; regenerated label on order 934242 with new tracking and history 'voided 9:27:05 AM, reissued 9:28:58 AM'. |  |  | 2026-10-18T04:01:40Z
RET-001 | Returns | P1 | positive | Return label (UPS Ground, Print, RMA, reason Defective, Return of 934224) | ADMIN | MKL246 | UI: New return form + carrier log | Clear, correct refusal or success | FAIL | Order 934274 GENERATED (RETURN LABEL tag). UPS request correct: ShipTo MKL with the real phone, ShipFrom the customer, ReturnService code 8, PO reference. But the form pre-fills the customer block with the merchant's own address and phone, shows the placeholder phone +1 555 123 6789 for 'Return to', and 'Return of #' does not load the original recipient. The label preview again shows the Bengaluru mock-up as ship-from. | BUG-011 |  | 2026-10-18T04:01:40Z
ERR-FIX-001 | Orders grid | High | positive | Failed order: Edit opens the fix form with the carrier's reason; Validate then Fix & regenerate buys the label on the same order number | ADMIN | MKL246 | UI: Orders > Edit on an ERROR order > change name > Validate > Fix & regenerate | Same order becomes GENERATED, no duplicate order | PASS | Order 934278 (UPS 120201, over-long recipient name): Edit opens 'Fixing failed order #934278 - Carrier rejected it: Missing or invalid ship to attention name' with every field prefilled. After shortening the name, Validate passed and 'Fix & regenerate' produced a UPS label on the same order 934278 (status GENERATED, no new order number, one carrier call logged). |  |  | 2026-10-18T04:19:32Z
GRID-COUNT-001 | Orders grid | Medium | positive | Tab badges (All / Ready / Pick account / Failed / Archive) add up to the number of rows the list actually returns | ADMIN | MKL246 | UI + API: compare tab badges, /orders/queue-stats, /orders/stats and GET /orders totals | Every order is counted in exactly one tab, and All equals the list total | FAIL | All orders badge shows 33,949 (sum of the other buckets, computed in the browser) while the list and /orders/stats report 33,957. Orders 900001, 900002, 900003, 900005 and 900006 show status ERROR (label FAILED) in the list but are missing from the Failed tab (493) and from the Error filter. | BUG-013 |  | 2026-10-18T04:15:12Z
GRID-FILTER-001 | Orders grid | High | positive | Advanced filters: Order #, Client code, Status, Source, Carrier narrow the list; Shipment vs return narrows it too | ADMIN | MKL246 | UI: Orders > Filters; network log checked after each change | Each filter refetches and narrows the list; badge counts it; Clear all resets it | FAIL | Order #, Client code (THB matches THB000), Status, Source (Bulk 3335 pages, API 0) and Carrier (DHL 0) all refetch immediately and filter correctly. 'Shipment vs return' does not: choosing 'Returns only' or 'Shipments only' sends no request and the rows stay the same. | BUG-012 |  | 2026-10-18T04:11:09Z
GRID-FILTER-002 | Orders grid | Medium | positive | Clear all resets every advanced filter, and the Filters badge counts every active filter | ADMIN | MKL246 | UI: Filters > set Returns only, set Status Error, click Clear all | All filters reset; badge reflects active filters | FAIL | After Returns only plus Status Error and a real click on Clear all, Status reset but Returns only stayed selected and the grid kept showing only returns (17 orders, 2 pages). Filters badge showed no count and Clear all was disabled, so nothing tells the user a filter is on. | BUG-012 |  | 2026-10-18T04:11:09Z
GRID-FILTER-003 | Orders grid | Medium | positive | Destination, Tracking #, Client code, Order #, Batch and date range filters match the right rows | ADMIN | MKL246 | UI + API replay of GET /api/v1/orders with each filter parameter | Filters narrow the list correctly | PASS | Destination (param city) matches city or 2-letter state, case-insensitive; Tracking # and Client code are contains-match, case-insensitive; Order # matches by prefix (9342 -> 80 rows); search prefixes order:, client:, batch:, tracking: work; createdFrom/createdTo are inclusive (18 Oct only -> 76 orders; 19 Oct -> 0). |  |  | 2026-10-18T04:15:12Z
GRID-FILTER-004 | Orders grid | Low | negative | Reversed or invalid date range gives a clear message | ADMIN | MKL246 | UI date inputs and API with bad dates | Inline message such as 'From date is after To date'; specific API error text | FAIL | From 19-10-2026 with To 18-10-2026 simply shows an empty table with no warning. The API returns 200 with 0 rows for a reversed range, a clear 400 for 'notadate', and a vague 400 ('This value can't be saved') for an impossible date such as 2026-13-45. | BUG-020 |  | 2026-10-18T04:15:12Z
BULK-001 | Bulk Mailer | High | positive | The app's own 'Plain CSV' template validates for MKL246 | ADMIN | MKL246 | UI: Bulk Mailer > Import > upload CSV built from the template; validation only, nothing saved | A template filled as documented validates, or the template shows the client's own ship-via codes | FAIL | The downloadable template (order-import-client-layout.csv) uses SHIPVIA_CD values FEDEX_GROUND and INTERNATIONAL_PRIORITY. Uploading the template rows unchanged (my valid.csv) gives '3 need fixes': every row fails with 'Service FEDEX_GROUND is not mapped for MKL246 ... a file import must use a Shipping Service Mapping rule'. The client only has F77 and P80 mapped. | BUG-014 |  | 2026-10-18T04:27:48Z
BULK-002 | Bulk Mailer | High | negative | Row validation catches each bad field with a clear, cell-level message (24 defect rows) | ADMIN | MKL246 | UI: upload QA-1018-bulk-invalid2.csv, read cell titles; nothing saved | Each defect reported on its row/cell | PASS | Missing/unknown client, other client without carrier account, empty recipient, bad/mismatched ZIP, bad state, missing city/address, weight 0/-3/abc/151 (150 lb limit named with the service), unknown country, phone 'abc', bad email, unknown/empty service, name over 50 chars: all flagged on the right cell with specific text. Duplicate recipient+reference only warns. Formula-looking name (=1+1) and PO Box accepted (ready). HTML angle brackets are silently stripped from values (script tags become 'scriptalert(1)/script'). |  |  | 2026-10-18T04:27:48Z
BULK-003 | Bulk Mailer | High | positive | Errors (CSV) download can be fixed and re-uploaded | ADMIN | MKL246 | UI: Errors (CSV) captured in page, one field fixed, re-uploaded via the file input; validation only | The documented fix-and-re-upload loop works | FAIL | The errors file uses the internal column layout (orderRef, clientCode, serviceType...) instead of the template layout, and rewrites the ship-via code F77 into the carrier code FEDEX_GROUND. Re-uploading a corrected errors file fails on every row with 'Service FEDEX_GROUND is not mapped for MKL246' (repro 2/2: 1-row and 2-row files). | BUG-014 |  | 2026-10-18T04:27:48Z
BULK-004 | Bulk Mailer | Medium | positive | Discard upload removes an unsaved upload and leaves Import history untouched | ADMIN | MKL246 | UI | Nothing persists after discard | PASS | Discard shows a confirm dialog, then 'Upload discarded'; the import list does not get a new entry. Upload counter advanced (Upload 8, 9, 10, 11) and the banner says 'kept until 10/25/2026'. |  |  | 2026-10-18T04:27:48Z
BULK-005 | Bulk Mailer | Medium | positive | Map ship via helper offers to create a mapping rule from the validation screen | ADMIN | MKL246 | UI, dialog opened and cancelled | Helper exists and explains the scope | PASS | Clicking 'Map FEDEX_GROUND...' opens 'Map ship via' with a carrier service picker and scope (Only MKL246 / every client). Cancelled without saving (creating a mapping rule is persistent config). |  |  | 2026-10-18T04:27:48Z
BULK-006 | Bulk Mailer | High | positive | Save to Import history creates the import with the right rows and keeps GROUP_ID as Ref # | ADMIN | MKL246 | UI: Save to Import history, Open import #11 | Import created, rows intact | PASS | 3 valid rows (F77, P80, lower-case p80) saved as import #11; grid shows Ref # QA-1018-BM-G1..G3, status PEND, no order numbers yet, 'Saved - not generated'. Lower-case ship-via code accepted. |  |  | 2026-10-18T04:34:32Z
BULK-007 | Bulk Mailer | High | positive | Generate labels from Import history creates orders and buys labels; failures are retryable per row | ADMIN | MKL246 | UI: Generate labels, Retry labels on import #11 | Orders created with source BULK and batch id; failed rows retryable | FAIL | Run created orders 934279 (FedEx, GENERATED, tracking 7948...4330), 934281 and 934280 (UPS). Both UPS calls timed out after 30 s on the first run (UPS CIE sandbox, HttpTimeoutException) and the rows went to Needs attention. Retry labels re-ran only the failed rows: 934281 generated, 934280 got UPS 9120000 'Ship web service is currently unavailable' (sandbox outage). Progress pill, Cancel and locked grid during the run all behaved. | BUG-015 |  | 2026-10-18T04:34:32Z
BULK-008 | Bulk Mailer | Medium | negative | Generate labels asks for confirmation before buying labels for the whole import | ADMIN | MKL246 | UI | Confirm step with the row count and carrier split | FAIL | One click on 'Generate labels' started purchasing for all rows immediately (no dialog). Orders grid 'Bulk labels' does show a confirm step. Cancel exists during the run. | BUG-016 |  | 2026-10-18T04:34:32Z
BULK-009 | Bulk Mailer | Medium | negative | Edge-case files: empty, header-only, no header, semicolon-delimited, UTF-8 BOM/unicode, binary named .csv, .txt, .exe, 1,200 rows | ADMIN | MKL246 | UI: in-page File objects set on the file input; every upload discarded | Clear refusal or correct parse | PASS | Empty, header-only, binary .csv and .txt: 'The file has no order rows'. No header: 'Failed to parse ...: A header name is missing in [row echoed]'. .exe: 'Only .csv, .txt, .xlsx and .xlsm files are supported' (server 415). Unicode with BOM: accepted, characters intact. 1,200 rows validated in 2.6 s with a virtualised grid. Semicolon-delimited file is parsed as one column (1 row, 10 errors) instead of a delimiter message (Low UX). |  |  | 2026-10-18T04:34:32Z
BULK-010 | Bulk Mailer | Medium | negative | Duplicate rows inside one file are flagged | ADMIN | MKL246 | UI | Warning or error on duplicates | PASS | Two identical rows (same recipient, address and reference) produce a warning on the second row ('same recipient, address and reference as row 19'); both still save. Reasonable. |  |  | 2026-10-18T04:34:32Z
BULK-011 | Bulk Mailer | Medium | positive | Import history lists imports with batch, counts and status; discarded uploads do not appear | ADMIN | MKL246 | UI /bulk/imports | Accurate list | PASS | Import #11 shows label batch 22, 'Partially Generated', 3 rows, 2 generated / 1 failed. Discarded uploads 8-10 and 12-14 are absent. Older imports from Sept show thousands of 'to fix' rows (test data). |  |  | 2026-10-18T04:35:13Z
BULK-012 | Bulk Mailer | Medium | positive | Labels & Invoices lists every labelled order with tracking, billed amount and the right documents (invoice only for international) | ADMIN | MKL246 | UI /bulk/labels (no downloads clicked) | Documents offered per order type | PASS | 33,457 labelled orders. Domestic rows offer Label, ZPL, Statement and say 'no invoice'; international rows (934265-934269) offer Invoice. Billed amounts match the carrier costs seen earlier (e.g. 934279 FedEx 21.56 USD). |  |  | 2026-10-18T04:35:13Z
APIB-001 | API Batches / D2C | High | negative | Fetch from WMS with the WMS datasource down fails safely with a clear message | ADMIN | MKL246 | UI: API Batches > Fetch from WMS, twice | Clear error, nothing created | PASS | POST /api/v1/wms/pull returns 502 'The WMS isn't reachable right now - check the WMS connection settings, then try the fetch again.' Toast 'Something went wrong' shows the same text; no batch is created. First click (the toast was missed in my capture) and second click both behaved the same. |  |  | 2026-10-18T04:36:47Z
APIB-002 | API Batches / D2C | High | positive | API batch intake, D2C automatic label and NDS scan (.X/.Y) flows | ADMIN | MKL246 | - | - | BLOCKED | No NDS/WMS data was provided and the Oracle datasource is OUT_OF_SERVICE for the whole run; the API Batches page is empty ('No API batches yet'). SSE /events/stream?topics=import-batches also answers 503. |  |  | 2026-10-18T04:36:47Z
D2C-001 | API Batches / D2C | Medium | negative | D2C Automatic Label page lists Oracle batches and Sync from Oracle fails safely while nds-default is inactive | ADMIN | MKL246 | UI /d2c/history, Sync clicked once | Clear, safe refusal | PASS | 87 historical D2C batches (client ARHDEV, Sep 29) with Print actions (not pressed). Sync from Oracle: POST /dtc/sync/oracle returns 409 'Oracle DTC sync is disabled. Enable the nds-default connection in Settings > External Systems.' shown in a toast. Note the request carries an empty tenantId query parameter. |  |  | 2026-10-18T04:37:16Z
D2C-002 | API Batches / D2C | High | positive | D2C Generate / Print on an Oracle batch | ADMIN | MKL246 | - | - | BLOCKED | Requires the nds-default (PROD-tagged) connection and a network printer. Not activated and nothing printed, per the agreed safety rules. |  |  | 2026-10-18T04:37:16Z
EOD-001 | Close out / pickups | Critical | positive | Close out day dialog lists today's open labels for the chosen carrier | ADMIN | MKL246 | UI: Orders > Close out day; API replay with several dates | Open labels listed so the operator can review before closing | FAIL | For 18 Oct 2026 the dialog shows 'Tracking numbers (0) - COULDN'T LOAD OPEN LABELS - TYPE THE NUMBERS' for FedEx, UPS and USPS. GET /api/v1/manifests/open?carrierCode=X&closeDate=2026-10-18 returns 500 INTERNAL_ERROR (reference ec042dc9) for all three carriers; the same call for 17 Oct returns 200 with 2 FedEx / 2 USPS trackings, and for 12 Sep (thousands of labels) returns 500 again. | BUG-017 |  | 2026-10-18T04:40:44Z
EOD-002 | Close out / pickups | High | positive | Close whole day / Close out selected (manifest with carrier) | ADMIN | MKL246 | - | - | BLOCKED | Not submitted: closing out is irreversible with the carrier and needs the user's go-ahead (asked in chat). Open-label listing is broken for today anyway (EOD-001). |  |  | 2026-10-18T04:40:44Z
EOD-003 | Close out / pickups | High | positive | Schedule a pickup (Settings > Pickups & End-of-Day) | ADMIN | MKL246 | - | - | BLOCKED | Form reviewed (carrier, client, date, service, window, address, parcels, driver instructions) but not submitted: a pickup request goes to the carrier and needs the user's go-ahead (asked in chat). POST /api/v1/pickups is the endpoint. |  |  | 2026-10-18T04:40:44Z
EOD-004 | Close out / pickups | Medium | positive | Manifest/pickup event history endpoint | ADMIN | MKL246 | API + UI | Consistent empty history | PASS | GET /api/v1/manifests/events?limit=5 returns 200 with an empty list ('No pickups or close-outs yet'), consistent with the Recent activity panel. |  |  | 2026-10-18T04:40:44Z
FUNDS-001 | Add Funds | High | positive | Add postage funds page shows balance, limit, presets and a correct charge preview (USPS account 7, sandbox) | ADMIN | MKL246 | UI /settings/carriers/7/add-funds, form only | Correct preview, submit withheld | PASS | Current balance $158.53, 'Can add up to $9,841.47' (Stamps.com $10,000 balance limit). Presets $25/$50/$100/$250 and a custom amount update 'You'll be charged' and 'New balance' (25.50 -> $184.03). Recent top-ups empty. Not submitted (money-moving; asked the user). |  |  | 2026-10-18T04:43:14Z
FUNDS-002 | Add Funds | High | negative | Custom amount validation: minimum $10, cents only, numeric, limit | ADMIN | MKL246 | UI form only | Clear refusals | PASS | 5 and 9.99 -> 'at least $10'; abc, -50, 0, blank -> no Add button; 25.555 -> 'Enter dollars and cents, like 25.50'; 9841.48 and above -> 'That would go over Stamps.com's $10,000.00 balance limit. You can add up to $9,841.47.' 1e3 is accepted as $1,000.00 (scientific notation). |  |  | 2026-10-18T04:43:14Z
FUNDS-003 | Add Funds | Low | negative | The advertised maximum top-up amount is accepted | ADMIN | MKL246 | UI form only | 9841.47 accepted | FAIL | Typing exactly 9841.47 (the amount the page says you can add) shows 'Enter dollars and cents, like 25.50' and hides the Add button; 9840.99 is accepted. Likely a floating-point comparison when balance + amount equals the limit exactly. | BUG-019 |  | 2026-10-18T04:43:14Z
FUNDS-004 | Add Funds | Medium | negative | Add funds on an account that is not yet authorized with Stamps.com is blocked | ADMIN | MKL246 | UI form only | Add button disabled until authorized | FAIL | Account 5 (USPS-STAMP TEST) shows 'This USPS account isn't authorized with Stamps.com yet. Click Authorize first' with balance '-', yet the amount presets and the 'Add $50.00' button stay enabled, including 'Add $1,000,000.00' for a custom amount (no upper limit without a known balance). Not pressed. | BUG-018 |  | 2026-10-18T04:43:14Z
FUNDS-005 | Add Funds | High | positive | Submit a top-up (Add $X) and verify the new balance and the Recent top-ups entry | ADMIN | MKL246 | - | - | BLOCKED | Withheld: money-moving submit. Waiting for the user's amount/account instruction (asked in chat). |  |  | 2026-10-18T04:43:14Z
SET-AB-001 | Settings | Medium | positive | Address book: add, edit, use in Ship to, remove (MKL246 entry) | ADMIN | MKL246 | UI /settings/address-book and /orders/new | CRUD works, validation on required fields | PASS | Empty-form save shows four inline 'Enter a ...' errors. Saved 'QA-1018 Address Book' for MKL246; edit added Suite 1018 and Residential; the New Shipment 'Search saved addresses' found it and filled every field including Suite and the Residential tick; Remove asked for confirmation ('Shipments already made are not affected') and the list went back to 'No saved addresses yet'. Nothing left behind. |  |  | 2026-10-18T04:47:54Z
DAT-TRK-001 | Data integrity | P2 | positive | Tracking numbers unique per label | ADMIN | MKL246 | API replay of POST /api/v1/orders/manual-label + order GET + carrier log check | Clear, correct refusal or success | BLOCKED | Of 28 labels, 16 share the UPS placeholder 1ZXXXXXXXXXXXXXXXX and 5 share one USPS number (sandbox behaviour); FedEx numbers are unique. Uniqueness can only be checked on production-like accounts. |  |  | 2026-10-18T03:52:30Z
PUR-DUP-001 | Data integrity | P1 | negative | Same reference/PO submitted twice (sequential) to manual-label | ADMIN | MKL246 | API replay of POST /api/v1/orders/manual-label | Clear, correct refusal or success | FAIL | Both calls bought a label: orders 934207 and 934208, same PO QA-1018-A001. No duplicate warning. | BUG-006 |  | 2026-10-18T03:38:54Z
PUR-DUP-002 | Data integrity | P1 | negative | Two identical manual-label requests sent at the same instant | ADMIN | MKL246 | API replay of POST /api/v1/orders/manual-label | Clear, correct refusal or success | FAIL | Both succeeded: orders 934209 and 934210, same PO QA-1018-A002. No idempotency key or lock. | BUG-006 |  | 2026-10-18T03:38:54Z
PUR-DUP-003 | Data integrity | P1 | negative | Double-click on Generate label in the New Shipment form | ADMIN | MKL246 | UI: New shipment form | Clear, correct refusal or success | PASS | One manual-label request and one order (934215, PO QA-1018-DC01); the second click did nothing. The form is protected; the gap is on the API side (see BUG-006). |  |  | 2026-10-18T03:41:07Z
PUR-DUP-004 | Data integrity | P2 | positive | Duplicate reference warning on Validate (API and reissue form) | ADMIN | MKL246 | UI + API replay | Clear, correct refusal or success | PASS | Validate returns WARN 'Reference ... already shipped on order #N (date). Make sure this isn't a second shipment of the same order.' Shown in the form on reissue too. |  |  | 2026-10-18T03:58:53Z
SEC-API-001 | Security | High | abuse | Orders list API robustness: oversized page size, bad sortBy, SQL metacharacters in search | ADMIN | MKL246 | API GET /api/v1/orders with hostile params | No 500, no SQL error leakage, bounded page size | PASS | size is clamped to 100; unknown sortBy and quote/semicolon payloads in search return a normal envelope, no 500, no SQL error text. search=% behaves as a wildcard (noted, Low). |  |  | 2026-10-18T04:06:01Z
SEC-AUTH-001 | Security | Critical | abuse | Unauthenticated access sweep: every /api/v1 endpoint refuses requests without the session cookie | ADMIN | MKL246 | fetch(path,{credentials:'omit'}) from the app origin | 401 for every protected resource | PASS | fetch with credentials omitted: /orders, /orders/934224, /clients, /carrier-accounts, /admin/carrier-api-log, /users, /shipping-services, /auth/session all return 401 UNAUTHORIZED envelope. /actuator/env¦metrics¦mappings¦loggers¦beans return 401. |  |  | 2026-10-18T04:06:01Z
SEC-AUTH-002 | Security | Medium | abuse | Public actuator endpoints expose minimal information only | ADMIN | MKL246 | fetch without cookie | No internal details to anonymous callers | PASS | /actuator/health is public and returns only {status, groups} (currently OUT_OF_SERVICE because the NDS datasource is down); /actuator/info returns {}. No component details or credentials leaked. |  |  | 2026-10-18T04:06:01Z
SEC-CSRF-001 | Security | High | abuse | State-changing POST without the XSRF header is refused | ADMIN | MKL246 | API POST /api/v1/shipments/validate with and without header | 403 without CSRF header | PASS | POST without X-XSRF-TOKEN returned 403 FORBIDDEN; with the header echoing the XSRF-TOKEN cookie it succeeds. |  |  | 2026-10-18T04:06:01Z
SEC-CSV-001 | Security | Medium | abuse | CSV export neutralises spreadsheet formula injection (=, +, -, @ at start of a cell) | ADMIN | MKL246 | UI: Orders grid > Export; capture Blob in page | Cells that start with = + - @ are escaped | PASS | Orders 934276/934277 with references starting with '=' exported with a leading apostrophe in the in-page captured CSV (nothing written to disk). |  |  | 2026-10-18T04:06:01Z
SEC-DOC-001 | Security | Low | abuse | Swagger / API docs not exposed on the UI origin | ADMIN | MKL246 | GET /swagger-ui.html | No API console for anonymous users | PASS | /swagger-ui.html on :5173 returns the SPA index.html (200 text/html), not an API console. Note: the proxy returns 200 for unknown paths (SPA fallback), which can confuse scanners and monitors. |  |  | 2026-10-18T04:06:01Z
SEC-HDR-001 | Security | Medium | abuse | Security response headers | ADMIN | MKL246 | Inspect response headers of an unauthenticated and an authenticated call | Standard hardening headers present | PASS | API responses carry Cache-Control no-store, Content-Security-Policy (default-src 'self'; frame-ancestors 'none'), X-Frame-Options DENY, X-Content-Type-Options nosniff, Referrer-Policy strict-origin-when-cross-origin, x-request-id. Note: error JSON is served as application/json;charset=ISO-8859-1 (Low). |  |  | 2026-10-18T04:06:01Z
SEC-ROLE-001 | Security | Critical | abuse | Role gating: USER and TENANT roles cannot reach admin settings, other clients' orders, or add funds | ADMIN | MKL246 | - | - | BLOCKED | No test logins were supplied (asked twice). The admin session was not logged out. Existing non-admin accounts (197609, smoke for MKL246; manoj7000 for THB000) exist but their passwords are unknown and 'Reset password' was not used. |  |  | 2026-10-18T04:47:54Z
SEC-SECRET-001 | Security | High | abuse | Secrets are not exposed in carrier-account or API-key responses and pages | ADMIN | MKL246 | API + UI review | No plaintext secrets | PASS | /carrier-accounts returns only clientIdPreview (masked, ...id) and no secret/token fields; GET /carrier-accounts/{id} is 405; /api-keys returns an empty list (no keys issued); /settings/api-keys shows 'No API keys yet'. Users page lists usernames and emails only (no hashes). /users and /roles API routes do not exist (404). |  |  | 2026-10-18T04:47:54Z
SEC-TEN-001 | Security | High | abuse | Tenant isolation by URL/ID tampering (read-only probes as ADMIN) | ADMIN | MKL246 | API GET with foreign client ids and malformed ids | Admin sees all; no stack traces; tenant users blocked (untested) | PASS | As ADMIN every client is visible by design: /clients/THB000, /clients/QA-1017-CL01, /orders/900674 (THB000) and its label, orders filtered by customer=THB000 all return 200. Unknown ids give clean 404s ('Client NOPE was not found', 'Order not found'); /orders/abc gives 400 'Parameter orderNo must be Integer'; /orders/-1 404. Role-based isolation (USER/TENANT) could not be tested: no test logins were provided. |  |  | 2026-10-18T04:47:54Z
SEC-XSS-001 | Security | High | abuse | Stored XSS: HTML/script payload in reference, name and address renders as plain text in orders grid, detail drawer and label page | ADMIN | MKL246 | UI + API: create order with HTML payloads in reference/name/address via manual-label; open Orders grid, Details drawer, label page | Payload shown as text, never executed | PASS | Payload (img/onerror and script tags) saved as text in order 934275; grid, detail drawer and /label/934275 show it escaped. Strict CSP meta (script-src 'self') also in place. Order went to ERROR because UPS rejected the string, which is expected. |  |  | 2026-10-18T04:06:01Z
VAL-API-016 | Security | P1 | negative | Special characters in recipient name: script tag, SQL, CRLF, emoji, RTL, NUL, =1+1 | ADMIN | MKL246 | API replay of POST /api/v1/shipments/validate (UI request body) | Clear, correct refusal or success | PASS | Validate accepts all (no reflection). Stored/rendered behaviour is tested in SEC cases after purchase. |  |  | 2026-10-18T03:38:54Z

## Bugs
ID | Severity | Area | Title | Steps to reproduce | Expected | Actual | Root cause / notes | Impact | Reproduced | Cases | Evidence | Environment | QA status | Dev status | Assigned to | Developer comments | Fixed in build
BUG-007 | High | New shipment > multi-box | Per-box declared values are ignored: the carrier gets box 1's value split evenly across all boxes | 1. New shipment, MKL246, UPS Ground, domestic. 2. Box 1: 4 lb 10x8x6, declared 80. 3. Add box 2 (2.5 lb, 12x9x4, declared 60) and box 3 (6 lb, 14x10x8, declared 40). 4. Validate, Generate. 5. Settings > Carrier API Log, filter by the order number, open the UPS ship request. | Each package goes to the carrier with its own declared value (80, 60, 40), total 180. | Order 934238: UPS request has DeclaredValue 26.67, 26.67 and 26.66 (box 1's 80 divided by 3). The form's request body does carry packages[].declaredValue 80/60/40 but the server ignores them. Repeated by API with two boxes declared 50 and 150: UPS order 934239 sent 25.00 and 25.00, FedEx order 934240 sent 25 and 25. |  | Silent wrong declared values on every multi-box shipment: carrier insurance/liability is understated (50 instead of 200 in the second test) or overstated per box, and declared-value surcharges are calculated on the wrong amounts. Operators see correct numbers on screen, so nobody notices. | 3/3 (UI 3-box UPS; API 2-box UPS; API 2-box FedEx) | SHP-MB-001, SHP-MB-002 | SHP-MB-001_three_box_ups_order_934238.jpg |  | Open
BUG-017 | High | Close out / pickups | Close out day cannot list today's open labels: GET /manifests/open returns 500 for busy dates, so the dialog falls back to 'type the numbers' | 1. Orders > Close out day. Leave Close date = today (18-10-2026), pick FedEx, UPS or USPS. 2. Watch the Tracking numbers panel: '(0) COULDN'T LOAD OPEN LABELS - TYPE THE NUMBERS'. 3. Change the date to 17-10-2026: FedEx lists 2 trackings, so the dialog itself works. 4. API: GET /api/v1/manifests/open?carrierCode=FEDEX&closeDate=2026-10-18 -> 500 INTERNAL_ERROR 'reference ec042dc9'; closeDate=2026-10-17 -> 200 [2 trackings]; closeDate=2026-09-12 -> 500. | Every open (generated, non-voided) label for the carrier and date is listed, however many there are. | The query fails whenever the date has more than a handful of labels (today has about 70, 12 Sep thousands). Dates with 0-2 labels work. Likely a non-unique-result or IN-list problem in the open-labels query (today also has many UPS labels sharing the sandbox tracking 1ZXXXXXXXXXXXXXXXX, but FedEx with unique trackings fails too). |  | The operator cannot review what will be manifested on the busiest days, exactly when the review matters. 'Close whole day' may still work server-side but was not run (irreversible with the carrier). | 3/3 carriers via UI, 5/5 API calls for 18 Oct and 12 Sep | EOD-001 | EOD-001_close_out_day_couldnt_load_open_labels_fedex.jpg, EOD-001_close_out_day_couldnt_load_open_labels_ups.jpg | ADMIN, localhost, server reference ec042dc9 in the logs | Open
BUG-001 | Medium | Label output | Label screen shows a fallback preview with the wrong Ship-From (Bengaluru default) and order number as REF when preview.png returns 503 | 1. Log in as ADMIN, open New shipment 2. Select client MKL246 (warehouse 3PL-EAST, sender MKL, 8191 Logistics Dr, Zeeland MI 49464) 3. Create a FedEx Ground or UPS Ground shipment with PO QA-1018-T001 / T002 and click Generate label 4. On the label page compare SHIP FROM and REF with the form | Preview shows the shipment's own sender (MKL, Zeeland MI) and its reference, or clearly says the image preview is unavailable | Preview shows SHIP FROM 'Multiship Warehouse, 1 Warehouse Way, Bengaluru, KA 560001' and REF = order number (934201 / 934202). HEAD /api/v1/orders/<id>/label/preview.png returns 503 and the UI falls back to a generic text label. The stored ZPL and the FedEx ship request carry the correct Zeeland sender, so only the on-screen preview is wrong. | The 'Multiship Warehouse, 1 Warehouse Way, Bengaluru, KA 560001' address is the platform default sender shown on a fresh New Shipment form before a client is chosen (the form badge reads 'IN -> US INTL'). The label page's mock-up preview (used because /label/preview.png returns 503) prints this default instead of the order's own sender; the carrier request and commercial invoice carry the right sender. |  | 6/6 (UI order 934205, 934206, 934202, 934201, return label 934274, fix flow label 934278) | LBL-001 | SHP-FDX-001_label_preview_934201.jpg, SHP-UPS-001_label_preview_934202.jpg, SHP-UPS-002_label_preview_934205.jpg, SHP-USP-002_label_preview_934206.jpg |  | Open
BUG-003 | Medium | Validation (server side) | Server accepts unusable phone numbers and emails that the New Shipment form rejects (API/validation gap) | 1. Log in as ADMIN. 2. POST /api/v1/shipments/validate with the body the New Shipment form sends (UPS Ground, MKL246) but recipient.phone = 'abc', then '12345', then '' ; separately recipient.email = 'not-an-email'. 3. Read data.overall. | Same rules as the UI (US phone 10 digits, phone required, valid email) or a clear refusal. | 'abc' and '12345' return overall PASS with a quote; empty phone returns WARN ('Recipient phone is recommended'); 'not-an-email' returns PASS. |  | Anything that bypasses the form (API integrations, the External API, bulk imports) can create shipments with unusable contact data. UPS requires a phone in production, so those become failed orders; bad emails break notifications. | Reproduced with two different invalid phone values ('abc', '12345') plus an invalid email | VAL-API-012, VAL-API-013 |  |  | Open
BUG-004 | Medium | Validation / label purchase | Validate says 'ready to ship' for over-long name, address and reference, then UPS rejects the label and an ERROR order is created | 1. Send the New Shipment body for UPS Ground (MKL246) to POST /api/v1/shipments/validate with recipient.name 120 chars and addressLine1 300 chars, then separately reference 300 chars. 2. Send the same bodies to POST /api/v1/orders/manual-label. | Validation refuses values longer than the carrier limit (35 characters for UPS name, address lines and reference), or the app truncates safely and says so. | Validate returns PASS for all three. manual-label then returns HTTP 502: UPS 120201 'Missing or invalid ship to attention name' (order 934213 saved as ERROR), UPS 120603 'Invalid Package Reference Value' for a 300-char reference (order 934214) and for a 36-char reference (order 934217). A 35-char reference works (order 934216). The New Shipment form lets the user type 80 characters in Reference / PO (maxlength 80) and has no maxlength on name, address or city, so 36-80 characters in the PO field always fails on UPS. |  | The Shipment Check promises the label will generate and then it fails at purchase. Operators waste a round trip and the grid fills with ERROR orders. If other carriers truncate silently, labels could print cut-off addresses. | 3/3 (name+address, 300-char reference, and the exact boundary: 35-char reference OK, 36-char reference rejected by UPS with code 120603) | VAL-API-014 |  |  | Open
BUG-006 | Medium | Label purchase (data integrity) | Label purchase endpoint accepts a second label for the same reference and for simultaneous requests; the duplicate check exists only as a Validate warning | 1. POST /api/v1/orders/manual-label with a valid UPS Ground body, reference QA-1018-A001. 2. POST the identical body again. 3. Separately, send two identical requests at the same moment with reference QA-1018-A002. | A duplicate within a short window is refused or needs confirmation (idempotency key, lock, or duplicate-PO warning). Only one label is bought for a double submit. | Validate does warn about duplicates ('Reference QA-1018-A001 already shipped on order #934208 (2026-10-18). Make sure this isn't a second shipment of the same order.') and the form blocks a double click, but POST /orders/manual-label itself enforces nothing. Sequential duplicate: orders 934207 and 934208, both GENERATED with the same PO. Two identical requests at the same instant: orders 934209 and 934210, both GENERATED. Each is a separate carrier purchase. |  | The UI path is reasonably protected (warning plus in-flight lock). Integrations or scripts that call manual-label (or the External API, still to be tested) without validating, and any retry after a timeout, can double-buy labels. On a live carrier account each extra label is a charge and a void/refund task. | 2/2 (sequential and concurrent) | PUR-DUP-001, PUR-DUP-002 |  |  | Open
BUG-008 | Medium | New shipment > price check | Shipment Check price leaves out signature and declared-value charges, so the label costs far more than the quote | 1. API replay of the form body (UPS Ground, 4 lb, 10x8x6, MI to NY 10118). 2. POST /shipments/validate and note data.quote.carrierAmount (11.33). 3. POST /orders/manual-label with signatureOption ADULT, then DIRECT, INDIRECT; separately with declaredValue 150, 200 and 500. 4. Compare shippingCost in the response. | The quote shown before purchase includes the accessorial fees for the options picked, or says clearly that they are excluded. | Quote is 11.33 in every case. Actual cost: base 11.44; adult signature 20.79; direct 19.14; indirect 19.14; declared 150 -> 16.34; 200 -> 16.54; 500 -> 19.94. Quote was equal to the plain base fare regardless of options. For insurance the check does warn ('adds a declared-value charge') but gives no number; for signature there is no warning at all. (Residential showed no surcharge on the sandbox label either.) |  | Operators and clients decide on service and options from a price that can be 45-80 percent too low. Margin and customer quotes are wrong; in production the difference is real money. | 3 signature levels and 3 declared values, all reproduced | OPT-ACC-001 |  |  | Open
BUG-011 | Medium | Returns | Return form pre-fills the customer ('Return from') block with the merchant's own address and phone, and 'Return of #' does not load the original recipient | 1. Orders > New return. 2. Select client MKL246 (Ship from 3PL-EAST). 3. Look at the 'Return from - customer' block. 4. Type an existing order number (934224) in 'Return of #' and wait. | Customer block is empty (or filled from the original order's recipient when Return of # is entered); 'Return to' shows the warehouse phone. | Customer block shows 8191 Logistics Dr, Zeeland MI 49464 and phone +1 616-772-3513 (the merchant's), only the name is empty. 'Return of #' 934224 changes nothing. 'Return to - your address' shows the placeholder phone +1 555 123 6789 (the carrier request later carries the correct +1 616-772-3513). |  | Validation passes as soon as the operator types a name, so a return label can be created from the merchant's own address to itself. A fake 555 number is displayed as the warehouse phone. | 2/2 form loads | RET-001 | RET-001_return_form_prefilled_customer_block.jpg |  | Open
BUG-012 | Medium | Orders grid | 'Shipment vs return' filter is silently broken: it does nothing on its own, then stays applied invisibly and survives 'Clear all' | 1. Open Orders, click Filters. 2. Choose 'Returns only' in 'Shipment vs return' (nothing else). 3. Watch the grid and the network log: no request is sent, rows do not change. 4. Now change any other filter, for example Status = Error: the request now carries isReturn=Y and the grid shows only returns. 5. Click 'Clear all': Status resets, 'Returns only' stays selected and the grid keeps showing only returns (17 of 33,949 orders). | Picking Returns only or Shipments only refetches at once. The Filters badge counts it. Clear all resets it, so the grid goes back to all orders. | The choice is ignored until another filter triggers a reload. The badge shows no count and Clear all is greyed out, so a user sees only 17 orders with no sign that a filter is active and no way to clear it except reopening the panel and picking 'Any'. The server filter itself works (GET /orders with isReturn=Y returns 17, N returns 33,940). |  | Operators looking for an order can believe it is missing. Support tickets about 'lost orders' are likely. Easy to fix: include isReturnFilter in the effect dependencies, the active-filter count and the reset handler. | 2/2 (script-driven change and real form input; second run also with a real click on Clear all) | GRID-FILTER-001, GRID-FILTER-002 | GRID-FILTER-001_returns_only_selected_grid_unchanged.jpg, GRID-FILTER-001_returns_only_hidden_no_badge.jpg, GRID-FILTER-001_after_clear_all_still_returns_only.jpg | ADMIN, MKL246 data, Chrome, localhost:5173 | Open
BUG-014 | Medium | Bulk Mailer | Bulk import template and Errors (CSV) export both use carrier service codes that the importer itself rejects, so the documented fix-and-re-upload loop cannot work | 1. Bulk Mailer > Import > download 'Plain CSV' template (rows use SHIPVIA_CD = FEDEX_GROUND / INTERNATIONAL_PRIORITY). 2. Upload the template rows for MKL246: every row fails 'Service FEDEX_GROUND is not mapped for MKL246 ... a file import must use a Shipping Service Mapping rule'. 3. Upload any file with mapped codes (F77/P80) plus one bad field, click Errors (CSV). 4. Fix the bad field in the errors file and upload it again. | The template validates as shipped (or shows the client's mapped codes), and an errors file, once fixed, re-imports cleanly. | The errors file is written in the internal layout (orderRef, clientCode, serviceType...) and the ship-via code is replaced by the resolved carrier code (F77 becomes FEDEX_GROUND). On re-upload every row fails on the service column. Only the in-grid cell editing path works. |  | Operators who follow the on-screen instruction 'fix or download what fails validation' lose the whole batch to a mapping error that is not theirs. Workaround: fix in the grid, or edit the original file and re-upload. | 2/2 for the round trip (1-row and 2-row errors files), 3/3 rows for the template | BULK-001, BULK-003 | BULK-001_template_codes_rejected_3_need_fixes.jpg, BULK-003_errors_csv_roundtrip_fails_on_service.jpg, BULK-003_errors_csv_roundtrip2_fails_on_service.jpg | ADMIN, MKL246, validation step only (nothing saved) | Open
BUG-015 | Medium | Data integrity | Carrier API Log entries written by bulk label runs have no order number, so bulk labels cannot be traced from the log | 1. Bulk Mailer > open import #11 > Generate labels (3 rows). 2. Settings > Carrier API Log: filter Order no. = 934279 (or 934281). 3. Compare with a manual label (order 934278): its UPS calls carry orderNo 934278. | Every carrier call made for an order is logged with that order number. | The six entries from the bulk run and retry (ids 2408-2413: FedEx 200 x2, UPS timeout x2, UPS 500, UPS 200) all have orderNo null. GET /admin/carrier-api-log?orderNo=934279 returns nothing. The entries exist but can only be found by time. |  | Support cannot pull the carrier request/response for a bulk order (the main evidence for disputes and carrier tickets). | 6/6 log entries across 2 runs (generate and retry) | BULK-007 | BULK-008_generate_partially_generated_ups_timeout.jpg, BULK-009_retry_labels_2_of_3.jpg | ADMIN, MKL246, import #11 / label batch 22 | Open
BUG-002 | Low | New shipment > Customs | Reason of export defaults to 'Sample' on every international shipment because every MKL246/THB000 carrier account carries shippingPurpose=SAMPLE; the form copies the account default when the field is empty | 1. New shipment, client MKL246, any carrier. 2. Choose a non-US recipient country (tried CA with UPS, GB with USPS). 3. Look at 'Reason of export' without touching it. 4. Complete the shipment and open the Commercial Invoice. | The field is blank (forcing a choice) or defaults to the usual commercial reason (Sale), unless the client has a saved customs profile that says otherwise. | 'Sample' is already selected (third option in the list, not the first). The invoice for orders 934205 and 934206 prints 'Reason for export: SAMPLE'. MKL246 has no customs profile (GET /clients/MKL246/customs-profiles returns an empty list), so the default is not coming from client data. | Confirmed in the form code (BUG-143 comment): setReasonForExport(cur ¦¦ matchedAccount.shippingPurpose). localStorage ms:lastReason is written but not used as the default (set to GIFT and the form still showed Sample). Accounts 1, 2, 5, 7 have shippingPurpose SAMPLE; account 14 has none. So this is account configuration plus a risky default: a sale shipment is declared as a sample on the commercial invoice unless the operator notices. Recommendation: default the account setting to SALE or leave it empty and make the field mandatory with no default. | Operators who do not notice the pre-filled field send commercial sales through customs declared as samples. That changes duty treatment and is a legal document, so errors can mean fines, held parcels or rejected clearance. | 2/2 fresh forms (UPS to Canada, USPS to United Kingdom) | SHP-UPS-002, SHP-USP-002 | SHP-UPS-002_commercial_invoice_934205.jpg, SHP-USP-002_commercial_invoice_934206.jpg |  | Open
BUG-005 | Low | Label purchase (API) | Label purchase trusts the request's carrierCode over the selected account, so a mismatch calls the wrong carrier and saves an ERROR order | 1. Send the New Shipment body for UPS Ground with the UPS account (id 2) to POST /api/v1/orders/manual-label but set carrierCode to FEDEX. 2. Repeat with a different reference. | 400 'carrierCode does not match the carrier account', no order, no carrier call. Validate should say the same. | Validate passes carrierCode FOO and FEDEX. manual-label returns HTTP 502 'FedEx rejected the credentials (NOT.AUTHORIZED.ERROR)...' and saves orders 934211 and 934212 with status ERROR. |  | API-only (the UI cannot produce this) but it lets a caller route a shipment through the wrong carrier integration and leaves error orders behind. The error text also tells the caller how the FedEx credentials are configured. | 2/2 (orders 934211, 934212) | VAL-API-021 |  |  | Open
BUG-009 | Low | New shipment > options | 'Insured value' is never sent to any carrier and the server does not enforce the form's insured <= declared rule | 1. API replay of the form body with declaredValue 80 and insuredValue 200 (then 300) for UPS, FedEx and USPS. 2. Open the carrier requests in Settings > Carrier API Log. | Either insured value reaches the carrier (extra declared-value coverage) or the field does not exist; server refuses insured above declared like the form does. | Validate returns WARN only and purchase succeeds. UPS request has PackageServiceOptions.DeclaredValue 80 (order 934229, 934235), FedEx declaredValue 80 (934236), USPS request has no value field (934234, 934237). The label cost does not change with insured value. In the form, insured above declared is refused, so the field can never add cover beyond the declared value. |  | The field suggests extra insurance ('beyond the carrier's free $100 tier') that never reaches the label. API callers can send an insured amount that is silently dropped. | 4/4 (UPS x2, FedEx, USPS) | OPT-INS-002 | CARRIER-LOG_ups_request_declared_value_934229.jpg, OPT-INS-001_insured_cannot_exceed_declared.jpg |  | Open
BUG-010 | Low | Void / reissue | USPS void shows a raw database error when the tracking number matches many labels, and looks labels up by tracking number instead of order or label id | 1. Create two or more USPS labels in the Stamps sandbox (it returns the same tracking number each time). 2. POST /api/v1/orders/{orderNo}/void for one of them. | The void targets that order's own label (label_id is returned by Stamps at purchase), or a clean message is shown. | HTTP 502 'USPS void call failed for 9400111969000940000011: Query did not return a unique result: 158 results were returned'. Seen for orders 934246 and 934247. |  | In the sandbox USPS labels cannot be voided at all. In production the same error would appear for any repeated tracking number, and the message exposes internal query details. | 2/2 (934246, 934247) | VOID-003 |  |  | Open
BUG-013 | Low | Orders grid | Five failed orders (label status FAILED) are invisible in the Failed tab and Error filter, and the All orders badge (33,949) disagrees with the list total (33,957) | 1. Open Orders: note the badges All orders 33,949, Ready 0, Pick account 5, Failed 493, Archive 33,451. 2. Scroll the All orders list to the last page: the grid paginates 33,957 rows (1 of 3396 at 10 per page). 3. Search order 900001 (also 900002, 900003, 900005, 900006): the row is shown with status ERROR. 4. Open the Failed tab or set Status = Error and search the same order: not found. | Every order sits in exactly one tab and the All badge equals the number of rows in All. | These five rows have orderDetails.status ERROR but labelDetails.status FAILED. The Error filter and the Failed bucket use the label status ERROR only, so the rows never show up where operators fix failed orders. The All badge is computed in the browser as the sum of the buckets, so it is 8 short of the real total (/orders/stats reports totalOrders 33,957 against 33,949 in its own buckets). The other 3 missing rows were not identified (possibly voided orders). |  | Failed orders that nobody can find in the Failed queue. They look like old development data (900xxx range), so production impact depends on whether the FAILED label status can still be written by current code (my own failed orders all used ERROR). | 5/5 orders | GRID-COUNT-001 |  | ADMIN, API replay in the logged-in session | Open
BUG-016 | Low | Bulk Mailer | 'Generate labels' on an import purchases labels for every row with a single click and no confirmation | 1. Bulk Mailer > Import history > open any saved import. 2. Click Generate labels once. | A confirm step showing how many labels will be bought (the Orders grid 'Bulk labels' button has one). | The run starts at once; the only way out is Cancel while it is running. On an import of 1,200 rows this buys 1,200 labels on a mis-click. |  | Money risk on production accounts; inconsistent with the Orders grid. | 2/2 (first run and Retry labels) | BULK-008 | BULK-007_import_11_rows_before_generate.jpg | ADMIN, MKL246 | Open
BUG-018 | Low | Add Funds | Add funds: the Add button stays enabled on an account that is not authorized with Stamps.com, and any amount is allowed when the balance is unknown | 1. Settings > Carrier Accounts > USPS-STAMP (TEST) > Add funds (/settings/carriers/5/add-funds). 2. Read the red note 'This USPS account isn't authorized with Stamps.com yet'. 3. Type 1000000 in Other amount. | Amount controls and the Add button disabled until the account is authorized; the limit check still applies. | 'Add $1,000,000.00' is enabled. Server behaviour not exercised (not pressed). |  | Confusing at best; depends on the server rejecting the call. | 2/2 page loads | FUNDS-004 | FUNDS-001_add_funds_unauthorized_account_5.jpg, FUNDS-002_add_1000000_enabled_on_unauthorized_account.jpg | ADMIN | Open
BUG-019 | Low | Add Funds | Add funds rejects the exact maximum amount it advertises (9841.47) with a wrong 'dollars and cents' message | 1. Open /settings/carriers/7/add-funds (balance $158.53, 'Can add up to $9,841.47'). 2. Type 9841.47 in Other amount. | Accepted, new balance $10,000.00. | 'Enter dollars and cents, like 25.50' and no Add button. 9840.99 works; 9841.48 gives the correct over-limit message. |  | Edge case only. | 2/2 | FUNDS-003 |  | ADMIN | Open
BUG-020 | Low | Orders grid | A reversed date range (From after To) silently shows an empty grid instead of a message | 1. Orders: set From = 19-10-2026 and To = 18-10-2026 (toolbar or Filters panel, both share the same fields). 2. Look at the grid. | Inline hint such as 'From date is after To date' (or the dates swapped). | Empty table, 'Nothing matches the current filters'. The API answers 200 with 0 rows for the reversed range; 'notadate' gives a clear 400, but an impossible date (2026-13-45) gives a vague 400 'This value can't be saved - check the form and try again'. |  | Operators think orders are missing. | 2/2 (UI and API) | GRID-FILTER-004 |  | ADMIN | Open

## Data-integrity
Check | Orders | Expected | UI | API / carrier log | DB (user-run SELECT) | Bug / note
Declared value per box | 934238 (UI, 3 boxes) | 80 / 60 / 40 | 80 / 60 / 40 (form) | 26.67 / 26.67 / 26.66 (UPS request) | pending (query A2) | BUG-007
Declared value per box | 934239 (API, UPS) / 934240 (API, FedEx) | 50 / 150 | 50 / 150 (request body) | 25 / 25 (carrier request) | pending (query A2) | BUG-007
Insured value | 934218-934237 | insured 100-500 | accepted | absent from every carrier request | pending (query A3) | BUG-009
Quote vs actual | 934229 etc. | quote 11.33 | quote 11.33 | 20.79 adult signature; 19.94 declared 500 | n/a | BUG-008
Status after void | 934242 | VOID | grid VOID | orderDetails.status GENERATED, labelDetails.status VOIDED | pending (query A7) | observation
Tab counts | all | 33,957 | All badge 33,949; buckets 493/5/33,451 | /orders/stats total 33,957 | pending (query A1) | BUG-013
Bulk carrier log linkage | 934279-934281 | orderNo set | n/a | carrier-log rows 2408-2413 orderNo null | pending (query A6) | BUG-015
Vanished order | 934213 | exists as ERROR | 404 | carrier-log 2200 references 934213 | pending (query A5) | open question
Duplicate references | 934207/934208, 934209/934210 | second refused | warn only | two labels bought | pending (query A4) | BUG-006
Close-out open labels | FedEx/UPS/USPS 2026-10-18 | list of today's labels | 'couldn't load open labels' | /manifests/open 500 | pending (query A8) | BUG-017

## Security
ID | Check | Result | Detail | Bugs
SEC-API-001 | Orders list API robustness: oversized page size, bad sortBy, SQL metacharacters in search | PASS | size is clamped to 100; unknown sortBy and quote/semicolon payloads in search return a normal envelope, no 500, no SQL error text. search=% behaves as a wildcard (noted, Low).
SEC-AUTH-001 | Unauthenticated access sweep: every /api/v1 endpoint refuses requests without the session cookie | PASS | fetch with credentials omitted: /orders, /orders/934224, /clients, /carrier-accounts, /admin/carrier-api-log, /users, /shipping-services, /auth/session all return 401 UNAUTHORIZED envelope. /actuator/env¦metrics¦mappings¦loggers¦beans return 401.
SEC-AUTH-002 | Public actuator endpoints expose minimal information only | PASS | /actuator/health is public and returns only {status, groups} (currently OUT_OF_SERVICE because the NDS datasource is down); /actuator/info returns {}. No component details or credentials leaked.
SEC-CSRF-001 | State-changing POST without the XSRF header is refused | PASS | POST without X-XSRF-TOKEN returned 403 FORBIDDEN; with the header echoing the XSRF-TOKEN cookie it succeeds.
SEC-CSV-001 | CSV export neutralises spreadsheet formula injection (=, +, -, @ at start of a cell) | PASS | Orders 934276/934277 with references starting with '=' exported with a leading apostrophe in the in-page captured CSV (nothing written to disk).
SEC-DOC-001 | Swagger / API docs not exposed on the UI origin | PASS | /swagger-ui.html on :5173 returns the SPA index.html (200 text/html), not an API console. Note: the proxy returns 200 for unknown paths (SPA fallback), which can confuse scanners and monitors.
SEC-HDR-001 | Security response headers | PASS | API responses carry Cache-Control no-store, Content-Security-Policy (default-src 'self'; frame-ancestors 'none'), X-Frame-Options DENY, X-Content-Type-Options nosniff, Referrer-Policy strict-origin-when-cross-origin, x-request-id. Note: error JSON is served as application/json;charset=ISO-8859-1 (Low).
SEC-ROLE-001 | Role gating: USER and TENANT roles cannot reach admin settings, other clients' orders, or add funds | BLOCKED | No test logins were supplied (asked twice). The admin session was not logged out. Existing non-admin accounts (197609, smoke for MKL246; manoj7000 for THB000) exist but their passwords are unknown and 'Reset password' was not used.
SEC-SECRET-001 | Secrets are not exposed in carrier-account or API-key responses and pages | PASS | /carrier-accounts returns only clientIdPreview (masked, ...id) and no secret/token fields; GET /carrier-accounts/{id} is 405; /api-keys returns an empty list (no keys issued); /settings/api-keys shows 'No API keys yet'. Users page lists usernames and emails only (no hashes). /users and /roles API routes do not exist (404).
SEC-TEN-001 | Tenant isolation by URL/ID tampering (read-only probes as ADMIN) | PASS | As ADMIN every client is visible by design: /clients/THB000, /clients/QA-1017-CL01, /orders/900674 (THB000) and its label, orders filtered by customer=THB000 all return 200. Unknown ids give clean 404s ('Client NOPE was not found', 'Order not found'); /orders/abc gives 400 'Parameter orderNo must be Integer'; /orders/-1 404. Role-based isolation (USER/TENANT) could not be tested: no test logins were provided.
SEC-XSS-001 | Stored XSS: HTML/script payload in reference, name and address renders as plain text in orders grid, detail drawer and label page | PASS | Payload (img/onerror and script tags) saved as text in order 934275; grid, detail drawer and /label/934275 show it escaped. Strict CSP meta (script-src 'self') also in place. Order went to ERROR because UPS rejected the string, which is expected.
VAL-API-016 | Special characters in recipient name: script tag, SQL, CRLF, emoji, RTL, NUL, =1+1 | PASS | Validate accepts all (no reflection). Stored/rendered behaviour is tested in SEC cases after purchase.
note | External Systems lists a single connection 'nds-default' tagged PROD / DEFAULT, type NDS_ORACLE, Inactive, last updated Oct 8 2026 by admin. User said NDS is a test copy; the tag says PROD. Tester will not activate or press Test on it. Needs user confirmation which NDS it points to.
note | index.html carries a strict CSP meta tag (script-src 'self', object-src 'self' blob:, frame-src 'self' blob:, connect-src 'self' ws: wss:) and the dev comment says auth moved to httpOnly cookies. Good. Note sessionStorage key ms:externalApiKey keeps an API key in the browser for the API reference Try-it box, and requests need the XSRF-TOKEN cookie echoed in X-XSRF-TOKEN (a POST without it returns 403 FORBIDDEN, which is correct).
note | /actuator/health is reachable without login and reports OUT_OF_SERVICE (liveness/readiness groups only). Fine for a load balancer, but it also tells anyone that the NDS datasource is down.
note | The API Reference page stores the API key typed into its Try-it box in sessionStorage (ms:externalApiKey) in plain text. XSS is mitigated by CSP, but the key survives in the browser tab until it is closed.

## Observations
Kind | Observation | Timestamp (UTC)
assumption | Environment is a test stack as confirmed by the user. Verified from the browser: carrier hosts are sandbox only (apis-sandbox.fedex.com, wwwcie.ups.com, api.testing.stampsendicia.com) and all 5 carrier accounts are marked SANDBOX. | 2026-10-18T03:10:19Z
assumption | Only the ADMIN session (user 'admin') is available. Super Admin, Operator (USER) and Tenant cases are BLOCKED until the user sends test logins. The tester never logs out of or changes the open admin session (no password known). | 2026-10-18T03:10:19Z
assumption | QA data is created under client MKL246 only. QA-1017-CL01 and THB000 get read-only probes. Prefix for everything created: QA-1018-. | 2026-10-18T03:10:19Z
limitation | The three reference checklists named in the skill (test-areas, data-integrity-and-security, report-template) were not in the synced skill copy; matrix built from SKILL.md phases, the app route map and shipping-domain knowledge. | 2026-10-18T03:10:19Z
limitation | Dashboard System status: oracleDataSource OUT_OF_SERVICE (/actuator/health returns 503). NDS prefill (.X/.Y scan), tracking write-back and WMS-fetch cases are BLOCKED by connectivity and by no NDS test data. | 2026-10-18T03:10:19Z
security | External Systems lists a single connection 'nds-default' tagged PROD / DEFAULT, type NDS_ORACLE, Inactive, last updated Oct 8 2026 by admin. User said NDS is a test copy; the tag says PROD. Tester will not activate or press Test on it. Needs user confirmation which NDS it points to. | 2026-10-18T03:10:19Z
observation | Role registry (Settings > Roles): USER=Operator (invitable), TENANT=Tenant customer (invitable), ADMIN (not invitable), SUPERADMIN (not invitable). Front-end maps a TENANT user to a tenant by upper-casing the username (roles.ts). Server-side tenant scoping must not trust this. | 2026-10-18T03:10:19Z
observation | Data volumes: 33,874 orders in total; THB000 holds 33,467, MKL246 414, QA-1017-CL01 0. Carrier split on dashboard FedEx 25,358 / UPS 7,929 / USPS ~100. Looks like migrated production-style history; confirm PII is masked in this environment (hypothesis, not verified). | 2026-10-18T03:10:19Z
observation | Carrier Accounts page: usage counts sit on MKL246 accounts (FedEx MKL-FEDEX 25,358 labels, UPS THB-UPS 7,929 labels) although MKL246 has only 414 orders and THB000 has 33,467 orders and no carrier accounts. Possible tenant attribution mismatch (hypothesis). Also column shows 'N labels' together with 'never used'. | 2026-10-18T03:10:19Z
observation | Previous QA rounds R4-R8 (Oct 12-17) are visible in Users > Recent admin actions and in order refs QA-1013-R5-*, QA-1017-R8-*; bug numbers reached at least BUG-052. User chose a fresh run for this report. | 2026-10-18T03:10:19Z
observation | Skill text mentions settings/shipping-service-mapping; that route does not exist in this build. Ship-method mapping lives under Settings > Code Maps (per-client ERP ship-via aliases) and Routing Rules. | 2026-10-18T03:10:19Z
observation | Importer / Broker: 0 profiles. New Shipment shows 'No importer/broker profile for US - set one up' and says international shipments need a profile before a label can generate. | 2026-10-18T03:10:19Z
observation | AI assist (Paste & autofill with AI, HS suggest) uses an OpenAI key stored in Settings > System. Address text goes to a third party; check what is sent and whether PII is masked. | 2026-10-18T03:10:19Z
observation | Alerts History contains S_SERA_MPS_ROLLBACK_VOID_FAILED ('Label could not be f...'): a multi-package USPS (SERA) rollback void failed in an earlier round. Orphan label risk to retest. | 2026-10-18T03:10:19Z
perf | FedEx sandbox rate-quote endpoint returned 503 after 12-13 s on 3 of 4 attempts today (8:41 and 8:51 AM). The app degrades gracefully (warns, still allows label) but the user waits 12-13 s for that message. Carrier-side, not an app defect. | 2026-10-18T03:22:10Z
observation | Sandbox tracking numbers are not unique: UPS CIE always returns 1ZXXXXXXXXXXXXXXXX and USPS PMI returns CJ000000005US (3 earlier orders share it). Anything keyed on tracking number (search, void, write-back) cannot be proven unique in sandbox; only FedEx sandbox returns distinct numbers. | 2026-10-18T03:22:10Z
ux | New shipment: for USPS the Label type has no default and Validate silently does nothing except an inline 'Required - pick a label type'; FedEx defaults to ZPL. Placeholder 'US' in each item's Origin box looks like a real value but the field is empty ('Country of origin is required'). | 2026-10-18T03:22:10Z
observation | Earlier candidates NOT reproduced on a clean form: (a) sender phone flip to +1 555 123 6789, (b) UPS service list staying domestic for a Canada destination. Both were artefacts of a stale form after a synthetic country selection. Dropped, not reported as bugs. | 2026-10-18T03:29:27Z
ux | New shipment, international: Reason of export defaults to Sample on a fresh form and flows onto the commercial invoice as 'Reason for export: SAMPLE'. A commercial sale printed as Sample is a customs-declaration risk. Seen once; re-check on the next fresh international form before reporting. | 2026-10-18T03:29:27Z
ux | Validate blocked by missing FTR exemption/AES ITN is explained only by a toast that vanishes in a few seconds; the field is at the top of the page and not highlighted, the Customs step pill stays grey. Easy to miss. | 2026-10-18T03:29:27Z
observation | UPS order shipViaDescription is null in the order JSON for ship via 65 (UPS Worldwide Saver) - check whether the Orders grid shows the service name. | 2026-10-18T03:29:27Z
observation | Request body for POST /api/v1/shipments/validate and /orders/manual-label is identical (1111 chars for a 1-box intl shipment): sender{name,company,phone,email,addressLine1/2,city,state,postalCode,countryCode,phoneCountryCode}, recipient{same}, isReturn, reference, carrierCode, accountNumber, accountId, serviceId, packagePresetId, length, width, height, dimUnit, weight, weightUnit, clientCode, warehouseCode, declaredValue, currency, labelImageFormat, items[{description,sku,hsCode,countryOfOrigin,quantity,unitValue,weight,boxSeq}], reasonForExport, incoterms, clearanceOption, ftrExemption. Usable for API replays of boundary and negative cases. | 2026-10-18T03:32:35Z
observation | Country combobox: keyboard selection (focus, type, Down, Enter with real key events) works and avoids needing mouse coordinates. | 2026-10-18T03:32:35Z
ux | USPS international: Incoterms select offers DDU but Validate then rejects it ('choose DAP or DDP'). Seen once; recheck on the next USPS intl form. | 2026-10-18T03:32:35Z
observation | Carrier API Log (Settings) works well as evidence source: GET /api/v1/admin/carrier-api-log?orderNo=N lists round trips, GET /api/v1/admin/carrier-api-log/{id} returns full request and response bodies. All carrier hosts in use are sandbox (wwwcie.ups.com, apis-sandbox.fedex.com, api.testing.stampsendicia.com). | 2026-10-18T03:52:30Z
security | index.html carries a strict CSP meta tag (script-src 'self', object-src 'self' blob:, frame-src 'self' blob:, connect-src 'self' ws: wss:) and the dev comment says auth moved to httpOnly cookies. Good. Note sessionStorage key ms:externalApiKey keeps an API key in the browser for the API reference Try-it box, and requests need the XSRF-TOKEN cookie echoed in X-XSRF-TOKEN (a POST without it returns 403 FORBIDDEN, which is correct). | 2026-10-18T03:52:30Z
observation | Shipping catalog (GET /api/v1/shipping-services) lists 31 services with per-service limits: FedEx and UPS 150 lb, USPS 70 lb; length+girth 165 in (FedEx/UPS), USPS GA 130, Priority 108, PMI 108, Express Intl 130. Real USPS Priority Mail International is limited to 79 in length plus girth; confirm the catalog value 108 with the carrier docs. | 2026-10-18T03:52:30Z
ux | Other UPS services in the quote list are shown as 'UPS 59' and 'UPS 13' (service codes without names) next to named services. | 2026-10-18T03:52:30Z
observation | Carrier errors reach the operator as the raw carrier text, including JSON fragments and reference ids (e.g. 'The carrier rejected the shipment: STAMPS createShipmentSera[pkg 1/1] HTTP 400: {"error_reference_id":...'). Settings has a Carrier Error Messages page; check whether unmapped errors fall back to raw JSON. | 2026-10-18T03:55:36Z
observation | FedEx concurrency: when several FedEx rate calls run at once the quote sometimes comes back not QUOTED while the label purchase still works. Seen on 5 of 12 concurrent calls; one call at a time always quoted. | 2026-10-18T03:55:36Z
observation | Earlier candidate 'sender phone flips to +1 555 123 6789' is explained: +1 555 123 6789 is the placeholder phone the Return form shows for 'Return to'. The server replaces it with the warehouse phone on purchase. It was not a New shipment bug. | 2026-10-18T04:01:40Z
observation | Order JSON keeps orderDetails.status GENERATED after a void while labelDetails.status is VOIDED; the grid derives VOID from the label. Integrations reading orderDetails.status will not see the void. | 2026-10-18T04:01:40Z
observation | Return body includes returnPickupRequested:true by default (returnType PRINT). No pickup call appeared in the carrier log for order 934274, so it seems unused for UPS Print Return; confirm it cannot book a real pickup in production. | 2026-10-18T04:01:40Z
perf | GET /api/v1/orders with size=100 returns about 1.7 MB because every row embeds the base64 ZPL label (about 17 KB per order). The grid should load list fields only and fetch label data on demand. | 2026-10-18T04:06:01Z
observation | The Vite proxy answers 200 text/html (the SPA shell) for unknown paths such as /swagger-ui.html, so link checkers and uptime monitors would see success for missing pages. | 2026-10-18T04:06:01Z
security | /actuator/health is reachable without login and reports OUT_OF_SERVICE (liveness/readiness groups only). Fine for a load balancer, but it also tells anyone that the NDS datasource is down. | 2026-10-18T04:06:01Z
security | The API Reference page stores the API key typed into its Try-it box in sessionStorage (ms:externalApiKey) in plain text. XSS is mitigated by CSP, but the key survives in the browser tab until it is closed. | 2026-10-18T04:06:01Z
observation | Error responses are served as application/json;charset=ISO-8859-1 while success responses use UTF-8. Non-ASCII text in error messages (names, addresses) may be mangled. | 2026-10-18T04:06:01Z
open-question | Orders list: 3 more rows are counted in totalOrders but belong to none of the buckets (ERROR 493 + GENERATED 33,451 + PENDING 5 = 33,949 versus 33,957). Five of the missing 8 are legacy orders with label status FAILED. Which statuses do the other 3 carry? SELECT suggestion for the DB batch: status counts grouped by order status and label status. | 2026-10-18T04:15:12Z
observation | Order filter 'Carrier' lists DHL although DHL is not a configured carrier; it returns 0 rows. Source=API returns 0 rows (no orders created through the External API exist in this database). | 2026-10-18T04:15:12Z
observation | Five PENDING orders (900004, 900047, 900048, 900055, 900057) have order status GENERATED but label status PENDING. They are the 'Pick account' tab. | 2026-10-18T04:15:12Z
open-question | Order 934213 (over-long recipient name, UPS 120201) was recorded as saved with status ERROR when created, but GET /orders/934213 now returns 404 while the carrier API log still shows its UPS call (log id 2200). The sibling error orders 934211, 934212, 934214, 934217 and the new 934278 still exist. Either the row was removed by something after creation, or it was never committed. Re-test: 934278 created the same way; check it again later. | 2026-10-18T04:20:00Z
observation | Bulk import strips '<' and '>' from cell values silently (script tags become 'scriptalert(1)/script'). Safe against markup, but a legitimate value such as 'Smith <Jones>' is altered without any warning in the grid. | 2026-10-18T04:27:48Z
ux | Bulk import 'Validation finished' toast and the step bar are clear. The 'kept until' retention date (7 days) is shown for each upload. Uploads 8-11 were created and discarded during QA; they should not appear in Import history. | 2026-10-18T04:27:48Z
observation | UPS CIE sandbox was unstable during the bulk run (two 30 s timeouts, then error 9120000 'Ship web service is currently unavailable'). The app surfaced it correctly as per-row failures and the retry worked for one of two. Not an application bug. | 2026-10-18T04:34:32Z
ux | A semicolon-delimited CSV is parsed as a single column: the row shows 10 'required' errors instead of 'unrecognised delimiter'. European Excel exports default to semicolons. | 2026-10-18T04:34:32Z

## Test data (cleanup)
What | Id | Where | State | Note | Created (UTC)
Order/label | 934201 | MKL246 | GENERATED (sandbox FedEx), ref QA-1018-T001, tracking 794893800699 | void at end if void works | 2026-10-18T03:16:42Z
Order/label | 934202 | MKL246 | GENERATED (sandbox UPS CIE), ref QA-1018-T002, tracking placeholder 1ZXXXXXXXXXXXXXXXX |  | 2026-10-18T03:16:42Z
Order/label | 934203 | MKL246 | GENERATED (sandbox USPS Ground Advantage), ref QA-1018-T003, tracking 9400111969000940000011 |  | 2026-10-18T03:22:10Z
Order/label | 934204 | MKL246 | GENERATED (sandbox FedEx International Priority US to GB), ref QA-1018-T004, tracking 794893801250 |  | 2026-10-18T03:22:10Z
order | 934205 | MKL246 orders / app DB | GENERATED | QA-1018-T005 UPS Worldwide Saver US->CA, sandbox label + commercial invoice | 2026-10-18T03:29:27Z
order | 934206 | MKL246 orders / app DB | GENERATED | QA-1018-T006 USPS Priority Mail Intl US->GB, sandbox label + invoice | 2026-10-18T03:32:35Z
order | 934207-934208 | MKL246 / app DB | GENERATED x2 | QA-1018-A001 UPS Ground duplicate-PO test (2 labels bought, sandbox) | 2026-10-18T03:39:33Z
order | 934209-934210 | MKL246 / app DB | GENERATED x2 | QA-1018-A002 concurrent duplicate test (2 labels, sandbox) | 2026-10-18T03:39:33Z
order | 934211-934212 | MKL246 / app DB | ERROR x2 | QA-1018-A003/A004 carrierCode FEDEX with UPS account | 2026-10-18T03:39:33Z
order | 934213 | MKL246 / app DB | ERROR when created (UPS 120201); row no longer exists (GET /orders/934213 returns 404) but carrier log 2200 still references it | QA-1018-L001 over-long name/address rejected by UPS | 2026-10-18T03:39:33Z
order | 934214 | MKL246 / app DB | ERROR | QA-1018-AAAA.. 300-char reference rejected by UPS | 2026-10-18T03:39:33Z
order | 934215 | MKL246 / app DB | GENERATED | QA-1018-DC01 UPS Ground, UI double-click test (1 order) | 2026-10-18T03:41:07Z
order | 934216 | MKL246 / app DB | GENERATED | QA-1018-BBBB.. 35-char reference boundary OK | 2026-10-18T03:42:01Z
order | 934217 | MKL246 / app DB | ERROR | QA-1018-CCCC.. 36-char reference rejected by UPS | 2026-10-18T03:42:01Z
order | 934218-934220 | MKL246 / app DB | GENERATED x3 | QA-1018-OPT0/OPT1/OPT2 UPS Ground accessorial cost tests | 2026-10-18T03:50:39Z
order | 934221-934233 | MKL246 / app DB | GENERATED x13 | QA-1018-S-UPS-*, O-*, D-* UPS Ground/3DS/2DA/NDA service, signature and declared value tests (934221-934233) | 2026-10-18T03:50:39Z
order | 934234-934237 | MKL246 / app DB | GENERATED x4 | QA-1018-INS300-* and USPS-COST: insured value tests on UPS/FedEx/USPS | 2026-10-18T03:50:39Z
order | 934238 | MKL246 / app DB | GENERATED | QA-1018-MB01 three-box UPS Ground via UI | 2026-10-18T03:50:39Z
order | 934239-934240 | MKL246 / app DB | GENERATED x2 | QA-1018-MB02 (UPS) and MB03 (FedEx) two-box tests | 2026-10-18T03:50:39Z
order | 934249-934269 | MKL246 / app DB | GENERATED x20, ERROR x1 (934262) | QA-1018-I-* international matrix (UPS 9, FedEx 6, USPS 6) | 2026-10-18T03:55:36Z
order | 934270-934273 | MKL246 / app DB | ERROR x4 | QA-1018-EMB-* embargoed destination tests (CU, KP, IR) refused by carriers | 2026-10-18T03:55:36Z
order | 934274 | MKL246 / app DB | GENERATED (return) | QA-1018-RET1 UPS return label, RMA QA-1018-RMA1, original 934224 | 2026-10-18T04:01:40Z
order | 934242 | MKL246 / app DB | GENERATED (reissued after void) | QA-1018-S-FDX-ES voided then reissued; 934240 voided (FedEx 2-box) | 2026-10-18T04:01:40Z
Order (XSS payload, ERROR) | 934275 | MKL246 / Orders | ERROR (carrier rejected) | HTML payload in reference/name/address | 2026-10-18T04:06:01Z
Order (CSV formula payload) | 934276 | MKL246 / Orders | GENERATED | reference starts with = | 2026-10-18T04:06:01Z
Order (CSV formula payload, ref =QA-1018-F1) | 934277 | MKL246 / Orders | ERROR | carrier rejected the reference | 2026-10-18T04:06:01Z
order | 934278 | MKL246 / app DB | GENERATED (UPS) after Edit > Fix & regenerate; was ERROR | QA-1018-L002 80-char recipient name rejected by UPS 120201, then fixed through the grid Edit flow | 2026-10-18T04:20:00Z
Bulk import | import #11 (staging 15), label batch 22 | MKL246 / Bulk Mailer import history | Partially generated | file QA-1018-bulk-valid2.csv, 3 rows | 2026-10-18T04:34:32Z
order | 934279 | MKL246 / Orders | GENERATED (FedEx, bulk) | QA-1018-BM-G1 | 2026-10-18T04:34:32Z
order | 934280 | MKL246 / Orders | ERROR (UPS sandbox 9120000) | QA-1018-BM-G3 | 2026-10-18T04:34:32Z
order | 934281 | MKL246 / Orders | GENERATED (UPS, bulk, after retry) | QA-1018-BM-G2 | 2026-10-18T04:34:32Z
Bulk staging uploads | 8-10, 12-14 (discarded) | MKL246 / Bulk Mailer | deleted via Discard | should not appear in Import history | 2026-10-18T04:34:32Z
order | 934241-934248 | MKL246 / app DB | GENERATED x8 (934246/934247 USPS void failed, BUG-010) | QA-1018-S-FDX-* and S-USP-* FedEx/USPS domestic service matrix | 2026-10-18T03:55:00Z
order | 934224 | MKL246 / app DB | GENERATED (UPS void rejected by sandbox) | QA-1018-S-UPS-* void test; also the original of return 934274 | 2026-10-18T03:55:00Z

## Screens
Route | Title | Status | Role | Note
/dashboard | Dashboard | loads |  | 503 from /actuator/health x2 because oracleDataSource OUT_OF_SERVICE; Setup health 3 to fix
/orders | Shipment & Label | loads |  | tabs All 33874 / Ready 0 / Pick account 5 / Failed 482 / Archive 33387
/orders/new | New Shipment | loads |  | Shipment/Return toggle; 6 steps: Shipment, Addresses, Service, Packages, Customs, Items
/orders/api-batches | API Batches | loads
/bulk | Bulk Mailer | redirects to /bulk/imports
/bulk/imports | Bulk Mailer | loads |  | ResizeObserver loop console noise; '9,728 failed' lines in import history
/bulk/import | Import | loads
/bulk/labels | Labels & Invoices | loads
/bulk/trash | Bulk Mailer trash | loads
/orders/history | (alias) | redirects to /bulk/imports |  | odd target for 'orders/history'
/d2c/history | D2C Automatic Label | loads
/track-orders | (alias) | redirects to /orders
/labels | (alias) | redirects to /orders
/generate-labels | (alias) | redirects to /orders
/clients | (alias) | redirects to /settings/clients
/carrier | (alias) | redirects to /settings/carriers
/carrier-connections | (alias) | redirects to /settings/carriers
/settings | All settings | loads
/settings/clients | Clients | loads
/settings/warehouses | Warehouses | loads |  | 2 warehouses: 3PL-EAST, QA-1017-WH01
/settings/carriers | Carrier Accounts | loads |  | 5 accounts, all SANDBOX; 3/5 ready; USPS platform account 'Check failed'
/settings/shipping-catalog | Shipping Catalog | loads
/settings/address-book | Address book | loads
/settings/importer-broker | Importer / Broker | loads |  | 0 profiles
/settings/importer-broker/new | New profile | loads
/settings/templates | Templates | loads |  | /settings/label-templates redirects here
/settings/custom-fields | Custom Fields | loads
/settings/routing-rules | Routing Rules | loads
/settings/reports | Reports | loads
/settings/webhook-subscriptions | Webhook subscriptions | loads
/settings/code-maps | Code Maps | loads
/settings/api-keys | API keys | loads
/settings/api-reference | API reference | loads
/settings/audit-log | Logs | loads
/settings/system | System settings | loads |  | 404 x2 on /api/v1/tenants/QA-1016-CL01/settings/nds.* (tenant not in client list)
/settings/users | Users | loads
/settings/carrier-limits | Carrier Shipping Limits | loads
/settings/output-destinations | Output Destinations | loads
/settings/printers | Printers | loads
/settings/external-systems | External systems | loads |  | nds-default tagged PROD, Inactive
/settings/dtc-scheduler | DTC Scheduler | loads |  | Scheduler is off
/settings/mail | Mail | loads
/settings/notification-templates | Email Templates | loads
/settings/notification-delivery-log | Email Delivery Log | loads
/settings/notifications | Notifications | loads
/settings/cutoffs | Cutoffs & Holidays | loads
/settings/pickups | Pickups & End-of-Day | loads
/settings/writeback-journal | Writeback Journal | loads
/settings/returns-analytics | Returns Analytics | loads
/settings/carriers-platform | Carriers (platform) | loads
/settings/alerts-history | Alerts History | loads |  | contains S_SERA_MPS_ROLLBACK_VOID_FAILED alert
/settings/carrier-api-log | Carrier API Log | loads |  | 2020 entries; sandbox hosts only
/settings/roles | Roles | loads
/settings/countries | Countries | loads
/settings/reasons-for-export | Reasons for Export | loads
/settings/currencies | Currencies | loads
/settings/carrier-error-messages | Carrier Error Messages | loads
/settings/carrier-dropdowns | Carrier Dropdowns | loads